## AI list
IMRBPB Action item list Rev 10 dated April 2016
N° | Action | IP | due date | responsible | closure Date/comments
04/01 | Provide workable definition of serious Injury to IMRBPB ( IP 68) | 68 | 06 IMRBPB | Tom Newcombe | Feb 2007 See 2007 PB position on IP 68 and MOM
04/02 | IP 72 (in relation with IP 48) position to be implemented in MSG3 document | 72 | next MSG3 doc rev | Ric Anderson | Feb 2007 No MSG3 change required
05/01 | TCH to provide to MPIG : - PPH extract regarding wear consideration in structure associated to IP 88 (Previously ref 79/05 ) - ways wear consideration has been addressed in the past in each programm. | 88 | March 06 | Kevin Berger | closed in Feb 07 see AI 05/02
05/02 | IP 88 (Previously ref 79/05 ) to be revised considering data received from AI 05/01for new presentation | 88 | 2006 IMRBPB | MPIG chairman | Feb 2007 see MSG3 rev 2007.1 proposal
05/03 | IP 44 (MRB Check Interval Escalations) Regulatory working group to be launch to issue proposal to industry for dicussion | 44 | first draft to be provide by PB to industry by end of 2007 | Tom Newcombe | April 08 guideline issue1
05/04 | collect any associated data in relation to IP 62 | 62 | end november 06 | Francis Jouvard | 2005-10-20
05/05 | IP 71 : "action performed by flight crew " new IP(s) to be proposed | 71 | 2010 PB | MPIG | closed with following CIP 2008 / 5- 2008 / 6 2008 / 7- presented during 2010 meeting
05/06 | Proposal from MPIG regarding IP 81 to be revised and MSG 3 revision to be proposed accordingly | 81 | March 06 | MPIG chairman | Feb 2007 see MSG3 rev 2007.1 proposal
05/07 | A draft letter of confirmation will be circulating amoung regulatories to come to an agreed proposal. | 83 | draft will be sent to board by end june 2008 common for each NAA | Cliff Neudorf | 31/03/2009 see template rev 2 attached to IP83
05/08 | Further investigations to take place between regulatories to come to a final proposal to addresse the concern raised by IP 86 (non regular operation) MPIG input would be appreciated | 86 | June 06 | Francis Jouvard | Feb 2007 IP closed see PB 2007 position
05/09 | Regulators need further discussion to come to a final position (approval of dual MRBRs) | 87 | added on 2008 agenda 1st WG with TCCA/FAA/EASA to be launched by Oct 08 to take place in Ottawa | TCCA | 31/03/2009
05/10 | Request from PB in IMRPB position on IP 80 (Lightning/HIRF MSG-3 analysis process revision) | 80 | 2006-03-01 | MPIG chairman | Feb 2007 see MSG3 rev 2007.1 proposal
07/01 | New IP to be proposed to extend the IP 86 intial subject |  | end 2008 | Francis Jouvard | April 2008,Closed, Open in error and has been closed
07/02 | New IP to clarify FD analysis in relation with IP 81 | 81 | 2009 PB | MPIG | closed through approval of IP 103
07/03 | Provide copy of IP 89 to certification office for harmonization with revision to AC 25-19 or equivalent. | 89 | mid 2007 | each NAA rep | April 2008 confirmed done by each NAA during April 08 meeting
07/04 | TCCA to determine the technical elements for consideration, in order to develop implementation procedure (in the frame of bilateral agreements) for the harmonisation of MRB activities | 90 | 2008 PB | TCCA | April 2008,closed. Position reviewed . The best approach is to have participating regulatory present at the MWG.
08/01 | Assess all IP for the need of completion of the colum "NAA Implementation Reference" of IP index list and provide ref of conecrned document |  | 2009 PB extended to 2012 PB | each AA | waiting for FAA ANAC input close through opening of 13/03
08/02 | MPIG will propose a list of terms related to IP 44 guideline | 44 | May 31, 2008 | MPIG | closed during 2008 PB
08/03 | Regulatory to define the proposed terms and amend the guideline as required trhough issue 2 | 44 | 2011-06-01 | Francis Jouvard | closed by publication of IP 44 guidline isue 3
08/04 | industry to invite IMRBPB to the development activity of a single data base | 93 | NA | MPIG | closed by invitation of the 3 AA to the Montreal meeting
08/05 | Industry to propose acceptable process / method which can address the requirement of the 2nd line of paragraph 7.5 of guideline document | 44 | end Jan 09 | MPIG | closed as per comments in 2009 PB MOM
08/06 | Demonstrate why the 2% deviation or an equivlent level of reliability should not be in the evolution guideline | 44 | November 08 | IMRBPB | closed during 2009 PB
10/01 | develop guidance for LUP / HUP (including non regular utilization) |  | 2012 PB | PB (TCCA) | closed based on 2012 IMRBPB decision that the utilisation windows is the area of concerned and as been adressed by IP 102
10/02 | TCCA to combine comments and send clean proposal to PB end may. | 97 | end May 10 | TCCA | closed revised proposal presented at IMRBPB 2011
11/01 | issue a new IP "Clarification of glossary Definitions for General Visual (GVI) Detailed (DET) and Special Detailed (SDI) inspections" including cleaning aspect for GVI and Tactile for DET |  | 2012 PB | EASA
12/01 | amend the IP procedure to include applicability concern add distribution of CIP to MPIG |  | 2012-08-01 | Raymond C.M. HUNG | closed based on Rev 5 of the IP procedure
12/02 | MPIG to supply comment on IP 83 letter of confirmation | 83 | 2012-07-01 | MPIG | closed based on submission of IND 2012-03
12/03 | PB to review and combine regulatory comments regarding ATA MSG3 rotorcraft original issue |  | end July 12 | PB (TCCA) | closed , all comments submitted has requested
12/04 | L/HIRF WG to considere L/HIRF task transfer in MSG 3 | 121 | 2013 IMRBPB | MPIG | closed action incorporated into CIP IND 2012-09
12/05 | Clarification of policy permitting the consolidation of task, Notify MPIG if the CIP will be redrafted | CIP TCCA 2012-01 IP 77 | 2012-09-01 | TCCA | closed through submission of CIP TCCA 2012-01
12/06 | To coordinate CIP IND 2012-01 and CIP TCCA 2011-2 (regarding AC25-19A) and to arrange a net meeting for june 27 or 28th. |  | 2012-06-01 | MPIG | closed based on the development CIP IND 2012-01 submitted at 2103 IMRBPB
12/07 | Coordinate A4A position on including MSG3 and IP 105 in the ARP document and answer to SAE letter reagrding SHM and IP 105 to be sent | 105 | 2012-07-01 | PB Chair | done between Paul CONN and PB chair
12/08 | Each IMRPBP members to suplly to RMPIG chair comments regarding MSG 3 Volume 2 |  | Agust 12 | IMRBPB | comments sent by each reg
12/09 | RMPIG to provided comments disposition and revised Vol 2 |  | Nov 1st 2012 | RMPIG | comment answer and final document provided in Nov 2012
12/10 | To coordinate the revised IP procedure with members authorities and MPIG |  | 2012-07-01 | PB Chair | closed through rev 5 of CIP procedure
12/11 | To distribute revised CIP IND 2011-07 (FEC 8 without task) to all Authorities members for comments |  | 2012-09-01 | IMRBPB | part of the agenda of 2013 IMRBPB
13/01 | IMRBPB to revise the charter to includ ref to IMRBPB technical working group |  | 2014-04-01 | IMRBPB | Closed in 2015 charter
13/02 | IMRPBP to revise the CIP template to include applicabilty for vol 1 and 2 of MSG 3 and retroactivity |  | 2013-08-01 | IMRBPB | closed on the 30/04/14 during IMRBPB by adding retroactive statement
13/03 | Assess all IP for the need of completion of the colum "NAA Implementation Reference" of IP index list and provide ref of concerned document |  | 2014-04-01 | IMRBPB | Closed with issue of IMPS in April 2016 - and the archiving of existing Ips
13/04 | include more details on distribution on CIP within the 60 days period within IP procedure |  | 2013-08-01 | IMRBPB | closed with Rev 5 approved the 30/04/14
13/05 | RMPIG to asses all IP's from 2011 onwards for implementation into vol 2 |  | 2013-06-01 | RMPIG | closed based on RMPIG chairperson review and mom
13/06 | IMRBPB to coordinate CIP IND 2008-03 within respectives certifications offices on acceptability of the concept PB position resulting will be provided to MPIG by Oct 13 |  | 2014-07-01 | IMRBPB | Open waiting for MPIG SWG feed back
13/07 | EASA to incorporate from IP 127 into letter of confirmation and coordinate input from IPB | 127 | 2013-12-01 | EASA | closed on the 30/04/14 with approval of the 2 new confirmation letter
13/08 | IMRBPB and MPIG to jointly develop the recommendation with CIP TCCA 2012-01 |  | 2013-10-01 | cliff Neudorf Tony Harbottle | closed on 06/12/2013 considering the CIP is rejected by PB in relation with CIP TCCA 2012-01 Consolidation of tasks
13/09 | MPIG to coordinate final comments on CIP EASA 2013-02 , EASA to confirm this position of comments before 24/05 and coordinate with IMRBPB |  | 2013-05-24 | Ralf Schneider | closed final agreed wording distributed through IP 135, closed , accepted and included in MSG 3 rev 2013.1
13/10 | revise IP 44 guideline section 3 with the new recommandation from IP 134 | 134 and 44 | 2014-06-01 | Jeff Phipps | Closed. Done when IP44 added to appendix of IMPS
13/11 | further develop CIP EASA 2013-01 - tolerance windows |  | 2014-12-01 | EASA | Closed - CIP withdrawn
13/12 | confirm on comments on IP 115 are incorporated in IP 129 | 115 and IP 129 | 2013-11-01 | MPIG | Closed
14/01 | IMRBPB MRB process standard to adress revision status and implementation of MSG3 (ref to IP 143 recommendation for ref) | 143 | 2014-12-01 | TCCA | Closed during issuance of IMPS April 2016
15/01 | Revise IP management procedure to cover post meeting revisions to agreed IPs |  | 2016-06-01 | TCCA | Open
16/01 | The analysis of maintenance functions. Following the discussions on CIP IND 2015-10 at the April 2016 PB, Authorities to discuss whether maintenance functions should be considered separately from operational functions, and report back to MPIG. IP 104 refers |  | 2017-04-01 | IMRBPB | Open