## RMP 2011-2014
Current rulemaking program | Task No. | Title | Changes from RMP 2010-2013 to RMP 2011-2014 (including consultation) | Pre-RIA score | Driver | R2 Environmental Protection R3 Flight Standards R4 Product Safety R5 ATM/Airport | Work method | Task leading to | Start date Year/Quarter |  | End date Year/Quarter |  | 2011 FTE | 2012 FTE | 2013 FTE | 2014 FTE
2011-2014 | 21058 | Systematic development of GM to Part-21 | New task. (I) Refer to Art 3(5) of EASA MB Decision 08-2007 | pre-RIA not required according to Art 3(5) of EASA MB Decision 08-2007 | Implementation improvements | R4 | Agency | Decision | 2011 | 01 | 2012 | 01 | 0.015 | 0.015
2011-2014 | 21059 | Environmental protection – classification of changes to a type design Modify GM21A.91 to clarify which noise/emissions changes lead to a major change | New task (I) | Pre-RIA and ToR not required according to Art 3(5) and 4(4) of EASA MB Decision 08-2007 | Environmental | R2 | Agency | Decision | 2010 | 04 | 2011 | 03 | 0.1
2011-2014 | 145017 | Control of suppliers of components, parts and appliances used in maintenance The issue of overseeing the work of suppliers of components needs to be addressed. Recent events, in Europe also, have shown that there is an issue that could have in some cases a serious effect on safety. The lack of control of suppliers is one cause. | Title changed | pre-RIA old format + B9 according to pre-RIA in the new format | Industry Request | R4 | Group | Opinion | 2011 | 01 | 2014 | 01 | 0.1 | 0.125 | 0.15 | 0.1
2011-2014 | 145024 | Functions of B1 and B2 support staff and responsibilities - link with sign off | New task. Moved from inventory to the RMP 2011-2014 (I+S) |  | Industry request | R4 | Group | Opinion | 2011 | 02 | 2014 | 01 | 0.1 | 0.15 | 0.15 | 0.05
2011-2014 | 145.006 | 145.A.30(j) Applicability of Appendix IV which permits the exemption of non-EU staff to comply with Part-66. Stakeholders disagree on this issue. There is a need to review this concern in order to reach a final decision. |  | pre-RIA old format | Industry Request | R4 | Group | Opinion | 2014 | 03 | 2016 | 01 |  |  |  | 0.1
2011-2014 | 145.012 (b) | Release to service Envisaged deliverable: A Decision amending AMC/GM to Part-M, Part-145 and Part-66 after amendment of these parts. | Ending date changed from 2011.01 to 2012.02 |  | Industry Request MS Request | R4 | Group | Decision | 2006 | 02 | 2012 | 02 | 0.1 | 0.075
2011-2014 | 145.022 | Control of contracted maintenance personnel (prg. 145.A30) |  | pre-RIA old format | Safety related | R4 | Group | Decision | 2009 | 03 | 2012 | 01 | 0.1 | 0.05
2011-2014 | 145.023 | Amendments (rule and AMC/GM) adapted to the process of granting foreign Part-145 approvals | Ending date changed from 2011.01 to 2012.02 |  | Certification request | R4 | Agency | Decision | 2009 | 01 | 2012 | 02 | 0.1 | 0.075
2011-2014 | 20.002 | Airworthiness and Operational Approval of Electronic Flight Bags: Update of AMC 20 to incorporate JAA TGL 36 taking into account technological developments. Envisaged deliverable: a decision amending AMC-20. | Task deleted from R.3 due to lack in resources but taken over by R.4 with 2011.04 as ending date (I) |  | Technological Development | R4 | Group | Decision | 2006 | 01 | 2011 | 04 | 0.025
2011-2014 | 20.006 (b) | Miscellaneous improvement to AMC 20 - Recognition of Eurocae ED-12B / RTCA DO-178B (JAA NPA 20-14) - Incorporation of JAA Leaflet 6 (RVSM), JAA Leaflet 7 (VHF 8.33 kHz), JAA Leaflet 8 (ACAS II), JAA Leaflet 10 (P-RNAV), JAA Leaflet 12 (TAWS), JAA Leaflet 13 (Mode S elementary Surveillance) and JAA Leaflet 17 (IFE systems) |  | B8 | Industry Request | R4 | Agency | Decision | 2006 | 02 | 2013 | 01 | 0.1 | 0.125 | 0.075
2011-2014 | 20.010 | Approval of Electronic Checklists Defining the conditions for airworthiness and operational approval of electronic checklists. | PS lead with FS involved | pre-RIA old format | MS request | R3 | Group | Decision | 2012 | 01 | 2014 | 02 |  | 0.125 | 0.125 | 0.063
2011-2014 | 20.010 | Approval of Electronic Checklists Defining the conditions for airworthiness and operational approval of electronic checklists. | Product Safety depart. lead with Flight Standards depart. involved | pre-RIA old format | MS request | R4 | Group | Decision | 2012 | 01 | 2014 | 02 |  | 0.075 | 0.15 | 0.1
2011-2014 | 20.014 | Guidance for the Determination of Flight Technical Error (FTE) Develop harmonised guidance material for the determination of FTE to include but not limited to - standardise some practical and realistic flight test scenarios - clarify the credit that can be taken from simulation to alleviate the flight test activities (agreed model for winds, gusts, …) - standardise the data reduction to retain max, average, or statistical deviations - standardise criteria for manual flying with Head Up Display and Flight Director - provide guidelines on the use of data-collection |  |  | Industry Request | R4 | Agency | Decision | 2013 | 02 | 2015 | 03 |  |  | 0.1 | 0.15
2011-2014 | 20.016 | Approval requirements for Air-Ground Data Link and ADS-B in support of Interoperability requirements | Title changed - Ending date changed from 2011.01 to 2011.03 |  | MS Request | R4 | Agency | Decision | 2009 | 03 | 2011 | 03 | 0.025
2011-2014 | 21.010 | 21A.3B Airworthiness Directives (AD’s) This paragraph will be reviewed in the light of discussions with NAAs and industry and to better align with the distribution of responsibilities as stipulated in the in the Basic Regulation also taking into account the amendment of the Basic Regulation. Examples of issues to be addressed are AMOCs and the possibility to issue ADs for engines, propellers and ETSO articles. This may lead to amendment of Part 21 and/or its AMC/GM | Ending date changed from 2011.01 to 2012.01 | pre-RIA old format | Safety related | R4 | Agency | Opinion | 2009 | 02 | 2012 | 01 | 0.1 | 0.05
2011-2014 | 21.017 | 21A.91 Classification of Changes |  | pre-RIA old format | Certification request | R4 | Group | Decision | 2013 | 04 | 2016 | 01 |  |  | 0.075 | 0.15
2011-2014 | 21.018 | Improvement of GM to 21A.101 |  | pre-RIA old format | Certification request | R4 | Agency | Decision | 2010 | 01 | 2011 | 01 | 0.075
2011-2014 | 21.023 (d) | Restricted CoA Clarification of the concept taking into account provisions of the Basic Regulation as well as previous work on Permit to Fly. Envisaged deliverables: decisions amending AMC/GM to Part 21 and AMC/GM to Part M. Depending on outcome of opinion on task 21.023(b) in 2009 RMP. | Ending date changed from 2011.01 to 2011.03. And then to 2012.01 (I) | pre-RIA old format | MS Request | R4 | Agency | Decision | 2007 | 01 | 2012 | 01 | 0.025 | 0.015
2011-2014 | 21.024 (a) | Subpart J DOA The objective is to better describe the privileges under 21A.263(b) and to review the related Agency obligations / responsibilities; this may lead to amending Part 21. | The task will deliver 2 Opinions - The first published in 2010/02 (on 19.05.2010) and the second in 2013/03 | pre-RIA old format | Industry Request | R4 | Group | Opinion | 2005 | 04 | 2013 | 03 | 0.025 | 0.025 | 0.025
2011-2014 | 21.024 (c) | Subpart J DOA - AMC/GM The objective is to better describe the privileges under 21A.263(b) and to review the related Agency obligations / responsibilities; this may lead to amending AMC/GM. | New task | pre-RIA old format | Industry Request | R4 | Group | Decision | 2005 | 04 | 2011 | 03 | 0.075
2011-2014 | 21.026 | New categories of parts for which Form 1 is not required: Revision of 21A.307 to establish an appropriate legal basis. |  | pre-RIA old format | Industry Request | R4 | Group | Opinion | 2011 | 01 | 2013 | 02 | 0.1 | 0.15 | 0.1
2011-2014 | 21.027 (b) | 21A.431(d) Changes and repair to ETSO article The objective is to make possible changes and repairs to ETSO articles outside ETSO authorization and to initiate the related amendment of Part 21 and/or its AMC/GM. Envisaged deliverable: a decision amending AMC/GM to Part 21. Depending on outcome of opinion on task 21.027(a) in 2009 RMP | Ending date changed from 2011.01 to 2011.03. And then to 2012.01 (I) | pre-RIA old format | Industry Request | R4 | Agency | Decision | 2006 | 04 | 2012 | 01 | 0.075 | 0.025
2011-2014 | 21.039 (a) | Elaboration and adoption in the Community framework, of additional airworthiness specifications for a given type of aircraft and type of operation. The objective is to specify the conditions under which an aircraft type has to be operated (MMEL, crew ratings, …) and maintained (engineers ratings, …), as well as specified equipments or devises that are to be fit on board the aircraft, to ensure full compliance with the essential requirement for airworthiness for any type of operation in which the aircraft may be engaged. Envisaged deliverable: an opinion proposing amendments to Part-21. The task will be finalised as 21.039(b) with the production of the related AMC/GM after amendment of Part-21. | Ending date changed from 2011.01 to 2011.02 |  | Safety related Legal obligation | R3 | Group | Opinion | 2007 | 03 | 2011 | 02 | 0.042
2011-2014 | 21.039 (a) | Elaboration and adoption in the Community framework, of additional airworthiness specifications for a given type of aircraft and type of operation. The objective is to specify the conditions under which an aircraft type has to be operated (MMEL, crew ratings, …) and maintained (engineers ratings, …), as well as specified equipments or devises that are to be fit on board the aircraft, to ensure full compliance with the essential requirement for airworthiness for any type of operation in which the aircraft may be engaged. Envisaged deliverable: an opinion proposing amendments to Part-21. The task will be finalised as 21.039(b) with the production of the related AMC/GM after amendment of Part-21. | Ending date changed from 2011.01 to 2011.02 | pre-RIA old format | Safety related Legal obligation | R4 | Group | Opinion | 2007 | 03 | 2011 | 02 | 0.3
2011-2014 | 21.039 (b) | Elaboration and adoption in the Community framework, of additional airworthiness specifications for a given type of aircraft and type of operation. Envisaged deliverable: a decision amending AMC/GM to Part 21. Depending on outcome of opinion on task 21.039(a) in 2009 RMP. |  | pre-RIA old format | Safety related Legal obligation | R4 | Group | Decision | 2007 | 03 | 2012 | 02 | 0.1 | 0.075
2011-2014 | 21.039 (c) | Elaboration and adoption in the Community framework, of additional airworthiness specifications for a given type of aircraft and type of operation. Envisaged deliverable: CS-MMEL for complex motor-powered aircraft. |  |  | Basic Regulation | R3 | Group | Decision | 2007 | 03 | 2012 | 02 | 0.125 | 0.063
2011-2014 | 21.039 (d) | Elaboration and adoption in the Community framework, of additional airworthiness specifications for a given type of aircraft and type of operation. Envisaged deliverable: CS-pilot type rating training. |  |  | Basic Regulation | R3 | Group | Decision | 2007 | 03 | 2012 | 02 | 0.125 | 0.063
2011-2014 | 21.039 (e) | Elaboration and adoption in the Community framework, of additional airworthiness specifications for a given type of aircraft and type of operation. Envisaged deliverable: CS-MCS - CS-maintenance certifying staff type rating training (importation of 66-011) |  |  | Safety related Legal obligation | R4 | Group | Decision | 2007 | 03 | 2012 | 02 | 0.1 | 0.075
2011-2014 | 21.039 (f) | Elaboration and adoption in the Community framework, of additional airworthiness specifications for a given type of aircraft and type of operation. Envisaged deliverable: CS-type specific data for cabin crew. |  |  | Basic Regulation | R3 | Group | Decision | 2007 | 03 | 2012 | 02 | 0.5 | 0.25
2011-2014 | 21.039 (g) | Elaboration and adoption in the Community framework, of additional airworthiness specifications for a given type of aircraft and type of operation. Envisaged deliverable: CS-data for evaluation of FSTD's. |  |  | Basic Regulation | R3 | Group | Decision | 2007 | 03 | 2012 | 02 | 0.125 | 0.063
2011-2014 | 21.039 (j) | Elaboration and adoption in the Community framework, of additional airworthiness specifications for a given type of aircraft and type of operation. Envisaged deliverable: CS-MMEL for other than complex motor-powered aircraft. |  |  | Basic Regulation | R3 | Group | Decision | 2007 | 03 | 2012 | 02 | 0.125 | 0.063
2011-2014 | 21.039 (k) | Additional airworthiness specifications for operations – Transposition of JAR-26 into CS-26 Envisaged deliverable: First issue of to CS-26. Depending on outcome of opinion on task 21.039(a) | Ending date changed from 2012.01 to 2012.03 - Work method changed - Title changed | B7 | Safety related Legal obligation | R4 | Agency | Decision | 2007 | 03 | 2012 | 03 | 0.1 | 0.125
2011-2014 | 21.041 | Part 21 Subpart H review The objective is to improve the drafting of current provisions and to establish guidance material to avoid recurrence of identified implementation problems. | Starting date changed from 2010.01 to 2010.04 | pre-RIA old format | MS Request | R4 | Group | Opinion | 2010 | 04 | 2013 | 03 | 0.1 | 0.15 | 0.125
2011-2014 | 21.046 | Replacement parts. Introduction of provisions allowing approval of replacement parts taking into account acceptance of PMA parts under the bilateral agreement with the US | Ending date changed from 2012.01 to 2012.02 | pre-RIA old format | Industry Request | R4 | Agency | Opinion | 2009 | 04 | 2012 | 02 | 0.1 | 0.075
2011-2014 | 21.047 | 3D models. Introduce guidance to make clear that TC applicant can use 3D models instead of 2D drawings. |  |  | Industry Request | R4 | Agency | Decision | 2013 | 01 | 2015 | 01 |  |  | 0.165 | 0.165
2011-2014 | 21.050 | Definition/clarification of the terms “Suspension, limitation and revocation”: implementing rules + AMC/GM. |  |  | Certification request | R4 | Agency | Opinion | 2013 | 03 | 2015 | 03 |  |  | 0.075 | 0.15
2011-2014 | 21.055 | Deteriorating Performance of Ageing Aircraft GM 21A.3B(b), paragraph 2.1.2.1 Flight |  | pre-RIA old format | MS Request Safety related | R4 | Agency | Decision | 2013 | 01 | 2014 | 02 |  |  | 0.165 | 0.1
2011-2014 | 21.056 | Permit to Fly issued by the Agency | Ending date changed from 2011.01 to 2011.02 |  | Legal obligation | R4 | Agency | Opinion | 2010 | 02 | 2011 | 02 | 0.075
2011-2014 | 22.006 | Sailplane and pilot rescue systems |  | pre-RIA old format | Safety related | R4 | Agency | Decision | 2012 | 01 | 2014 | 01 |  | 0.075 | 0.15 | 0.04
2011-2014 | 22.009 | Ground loads |  | pre-RIA old format | Industry request | R4 | Agency | Decision | 2011 | 01 | 2013 | 01 | 0.1 | 0.125 | 0.05
2011-2014 | 22.010 | Incorporation of special conditions in CS-22 | Starting date changed from 2011.03 to 2012.03 and ending date from 2013.01 to 2014.01 | pre-RIA old format | Certification request | R4 | Agency | Decision | 2012 | 03 | 2014 | 01 |  | 0.05 | 0.15 | 0.075
2011-2014 | 23.005 | High performance aeroplanes Develop certification specifications in CS-23 suitable for all jet and high- performance aeroplanes with a MTOW up to 8618 kg and for closely related technical developments | Starting date moved from 2009.01 to 2010.02 and ending date from 2012.01 to 2012.03 | pre-RIA old format | Industry Request | R4 | Agency | Decision | 2010 | 02 | 2012 | 03 | 0.1 | 0.125
2011-2014 | 23.010 | Consideration of the spin resistant concept in CS-23 Issue resulting from the discussions on the Special Condition for Cirrus S-20 aircraft. Consideration of a need for a ETSO for ballistic parachute rescue system |  | pre-RIA old format | Industry Request | R4 | Group | Decision | 2014 | 03 | 2016 | 02 |  |  |  | 0.1
2011-2014 | 23.014 | Incorporation of special conditions in CS-23 incl Diesel Engine installations |  | pre-RIA old format | Certification request | R4 | Agency | Decision | 2012 | 01 | 2013 | 03 |  | 0.075 | 0.075
2011-2014 | 25.011 | Flight Test Guide developments - Pilot Induced Oscillation: Develop harmonized CS/FAR 25 and AMC/AC - Handling Assessments using CS/FAR 25.1309/FAA HQRM: Develop harmonized Flight Test Guide material relating to the FAA's Handling Qualities Rating Method. - Flight Test procedures for Flight Guidance Systems coming from new draft AMC to Cs 25.1329 - Pilot reaction time to in-board engine failure - Landing distance on wet runway |  | pre-RIA old format | Industry Request | R4 | Agency | Decision | 2014 | 03 | 2016 | 01 |  |  |  | 0.1
2011-2014 | 25.026 | Electronic Checklists, smart alerting and automatic altitude call-outs: The objective is to amend CS-25 to introduce requirement aiming at reducing approach and landing accidents by: - Implementing interactive electronic checklist and smart alerting systems in new type-certificated airplanes. Consider FAA AC 120-64 and operational approval of electronic checklists. - Incorporating human factors principles into checklist design for new type-certificated airplanes. - Developing requirements for automatic aural altitude call-outs on final approach |  | pre-RIA old format | Safety related | R4 | Group | Decision | 2012 | 01 | 2014 | 01 |  | 0.075 | 0.15 | 0.05
2011-2014 | 25.027 | Aircraft Design: The objective is to amend CS-25 to introduce requirement aiming at reducing approach and landing accidents by: - Identifying flight-critical system components as the basis for design guidance, continuing airworthiness, and maintenance - Issuing design guidance to ensure flight-critical system components are fault tolerant and are subjected to critical-point, flight-realistic-condition, certification testing/analysis. - Linked to task 25.026 and task 25.029 (phase 2 on 25.1309). |  | pre-RIA old format | Safety related | R4 | Group | Decision | 2012 | 01 | 2014 | 03 |  | 0.075 | 0.15 | 0.1
2011-2014 | 25.028 | Protection From Debris Impacts and Fire Develop a new paragraph of CS/FAR-25, which would cover the protection of the whole aircraft against the threat of tire/wheel failure. Identified as a common priority for JAA-FAA-TCCA joint rulemaking Landing gear mechanism. Harmonisation activity on 25.729 (a) plus AMC based on JAA NPA 25D-163 |  | pre-RIA old format | Safety related | R4 | Group | Decision | 2009 | 01 | 2013 | 01 | 0.1 | 0.125 | 0.05
2011-2014 | 25.029 | 25.1309 - Phase 2 activites Consider the Phase 2 recommendations from the Systems Design and Analysis Harmonisation Working Group (SD&A HWG) for specific improvements and additions to CS/FAR 25.1309 related items. | Starting date moved from 2010.02 to 2010.03 | pre-RIA old format | Safety related | R4 | Agency | Decision | 2010 | 03 | 2013 | 01 | 0.1 | 0.15 | 0.05
2011-2014 | 25.031 | FAR 25 Amendment 87: Harmonization activity on CS/FAR 25.831(g)/841(a) on high altitude operations coming from FAR 25 Amendment 87. Harmonisation on relevant structure paragraphs |  | pre-RIA old format | Industry request | R4 | Agency | Decision | 2012 | 01 | 2014 | 01 |  | 0.075 | 0.15 | 0.05
2011-2014 | 25.035 | Cabin environment – Air Quality: A-NPA to decide on a possible EASA Rulemaking plan | Ending date changed from 2011.03 to 2012.01 | pre-RIA old format | MS Request | R4 | Group | Decision | 2009 | 01 | 2012 | 01 | 0.075 | 0.25
2011-2014 | 25.037 (a) | Avionics: Harmonization on a revised 25.1322/AMC on flight crew alerting and AMC 25-11 on electronic display systems in co-ordination with HF HWG |  | pre-RIA old format | Safety related | R4 | Agency | Decision | 2007 | 04 | 2011 | 01 | 0.025
2011-2014 | 25.039 | Type and number of Passenger Emergency Exits Proposed JAA NPA 25.298 (initial issue) introduces the FAA Amendment 25-88, revising the standards for the subject Emergency Exits. Rev. 1 to the above JAA NPA introduces difference with FAR Amendment 25-88: prohibition of non-floor level over wing exits in airplanes with more than 299 passengers. A Regulatory Impact Assessment will be developed. | Ending date changed from 2012.01 to 2012.02 | pre-RIA old format | Safety related | R4 | Agency | Decision | 2009 | 01 | 2012 | 02 | 0.1 | 0.05
2011-2014 | 25.044 | Screening of current cabin safety paragraphs The current set of cabin safety related airworthiness paragraphs does not in all cases reflect today’s technological standards in two ways: the question can be asked whether they have contributed as predicted to safety, and whether they can not be improved, simplified or even be deleted completely. Preparatory work will consist of a review of existing literature and research and of the development of a regulatory Impact Assessment. |  |  | Safety related | R4 | Agency | Decision | 2013 | 04 | 2016 | 01 |  |  | 0.0495 | 0.15
2011-2014 | 25.055 | Fuel System Low Level Indication / Fuel Exhaustion: Design improvements cannot be overlooked in favour of only operational changes. Recent incidents show the importance of improving such requirements. |  | pre-RIA old format | Safety related | R4 | Group | Decision | 2009 | 02 | 2012 | 01 | 0.1 | 0.05
2011-2014 | 25.057 | Security: The objective is to put CS-25 in line with ICAO amendments 97 and 99. Additional security needs shall be investigated at the same time and incorporated in CS 25 as appropriate. | Ending date moved from 2012.01 to 2011.01 | pre-RIA old format | MS Request | R4 | Agency | Decision | 2009 | 01 | 2011 | 01 | 0.075
2011-2014 | 25.058 | Large Aeroplane Certification Specifications in Supercooled Large Drop, Mixed phase, and Ice Crystal Icing Conditions Review National Transportation Safety Board recommandations A-96-54, A-96-56, and A-96-58, and advances in ice protection state-of-the-art. In light of this review, define an icing enviroment that includes supercooled large droplets (SLD), and devise requirements to assess the ability of aircraft to safely operate either for the period of time to exit or to operate without restriction in SLD aloft, in SLD at or near the surface, and in mixed-phase conditions if such conditions are determined to be more hazardous than the liquid phase icing environment containing supercooled water droplets. Consider the effects of icing requirement changes on 14 CFR Part 25 and revise the regulations if necessary. In addition, consider the need for a regulation that requires installation of a means to discriminate between conditions within and outside the certification envelope. | Ending date moved from 2013.03 to 2012.02 - Title changed | pre-RIA old format | Safety related | R4 | Agency | Decision | 2010 | 02 | 2012 | 02 | 0.1 | 0.075
2011-2014 | 25.067 | Flight Test Guide Publish a CS-25 Flight Test Guide which is a compilation of acceptable means of compliance for performance and handling qualities requirements | It has been decide to keep "Agency" as working method because the text is already available | pre-RIA old format | MS Request | R4 | Agency | Decision | 2011 | 01 | 2013 | 01 | 0.1 | 0.15 | 0.05
2011-2014 | 25.069 | The Crashworthiness of Composite Structures in Large Transport Aeroplanes |  |  | Certification request Safety related | R4 | Group | Decision | 2013 | 01 | 2015 | 03 |  |  | 0.15 | 0.15
2011-2014 | 25.070 | Incorporation of generic SC and AMC/GM in CS-25 | Starting date changed from 2009.03 to 2010.01 and ending date changed from 2011.01 to 2011.03 - Title changed - Ending date changed to 2012.01 (I) | pre-RIA old format | Certification request | R4 | Agency | Decision | 2010 | 02 | 2012 | 01 | 0.1 | 0.125
2011-2014 | 26.001 | Additional airworthiness specifications for operations: Type III Emergency exit access and ease of operation | Starting date changed from 2009.02 to 2010.02 and ending date changed from 2012.01 to 2012.03 - Title and Method changed | B8 | Safety related | R4 | Group | Decision | 2010 | 02 | 2012 | 03 | 0.1 | 0.125
2011-2014 | 26.002 | Seat crashworthiness improvement on Large Aeroplanes - Dynamic testing 16g | Starting date changed from 2009.01 to 2010.02 and ending date changed from 2012.01 to 2012.03 | A12 | Safety related | R4 | Agency | Decision | 2010 | 02 | 2012 | 03 | 0.1 | 0.125
2011-2014 | 26.003 | Fire hazard in Class D Cargo Compartments | Ending date changed from 2012.01 to 2012.03 | B12 | Safety related | R4 | Group | Decision | 2010 | 02 | 2012 | 03 | 0.1 | 0.125
2011-2014 | 26.004 | Additional airworthiness specifications for operations: Thermal/Acoustic Insulation Material | Title and Work Method changed | B8 | Safety related | R4 | Agency | Decision | 2010 | 02 | 2013 | 01 | 0.1 | 0.125 | 0.05
2011-2014 | 26.005 | Class B/F Cargo Compartment |  |  | Safety related | R4 | Agency | Decision | 2012 | 01 | 2014 | 01 |  | 0.075 | 0.15 | 0.05
2011-2014 | 26.006 | Reinforced cockpit doors - Dble incapacitation |  |  | Safety related | R4 | Agency | Decision | 2013 | 01 | 2016 | 01 |  |  | 0.125 | 0.15
2011-2014 | 26.008 | Production cut-in and retrofit of flammability reduction means | Starting date chnaged from 2009.02 to 2010.02 and ending date changed from 2012.01 to 2012.03 |  | Safety related | R4 | Agency | Decision | 2010 | 02 | 2012 | 03 | 0.1 | 0.125
2011-2014 | 27&29.002 (a) | Damage Tolerance & Fatigue Evaluation of Metallic Rotorcraft Structures This task results from the JAA/FAA harmonization programme and aims at: - Developing design methodologies for fatigue evaluation of metallic components and amending 27/29.571. | Title changed - Ending date changed from 2012.01 to 2011.03 | pre-RIA old format | Safety related | R4 | Agency | Decision | 2004 | 03 | 2011 | 03 | 0.0151
2011-2014 | 27&29.002 (b) | Damage Tolerance & Fatigue Evaluation of Composite Rotorcraft Structures This task results from the JAA/FAA harmonization programme and aims at: - Developing design methodologies for fatigue evaluation of composite components and creating a new 27/29.573. | Title changed - Ending date changed from 2013.01 to 2011.03 | pre-RIA old format | Safety related | R4 | Agency | Decision | 2004 | 03 | 2011 | 03 | 0.05
2011-2014 | 27&29.003 | Yawing Condition: Review and further develop CS 27/29.351 and develop AMC as appropriate | Ending date changed from 2012.01 to 2012.02 | pre-RIA old format | Certification request Safety related | R4 | Group | Decision | 2006 | 02 | 2012 | 02 | 0.1 | 0.075
2011-2014 | 27&29.008 | Ditching Occupant Survivability: Harmonized activity to develop enhanced design standards associated with helicopter ditching on water |  | pre-RIA old format | Safety related | R4 | Group | Decision | 2012 | 01 | 2015 | 01 |  | 0.075 | 0.15 | 0.15
2011-2014 | 27&29.018 | Helicopter tailrotor failures Recent research studies show that higher failure rates are discovered. To address this issue, it was recommended introducing additional requirements in the Certification Specification 27 and 29. UK CAA has provided the report substantiating the new task. |  | pre-RIA old format | Safety related | R4 | Agency | Decision | 2013 | 04 | 2016 | 01 |  |  | 0.0495 | 0.15
2011-2014 | 27&29.019 | VHM specification & update of MG15: Adoption of the VHM specification developed by the Helicopter Health Monitoring Advisory Group (HHMAG) and update to existing AC on HUMS (CS-27 MG15 and CS-29 MG15). | Ending date changed from 2011.01 to 2011.02 Ending date changed from 2011.02 to 2012.01 (I) | pre-RIA old format | Safety related | R4 | Group | Decision | 2007 | 04 | 2012 | 01 | 0.025 | 0.015
2011-2014 | 27&29.023 | Incorporation of special conditions in CS-27&29 |  | pre-RIA old format | Certification request | R4 | Agency | Decision | 2011 | 03 | 2013 | 01 | 0.05 | 0.125 | 0.05
2011-2014 | 27&29.027 | Helicopter H-V Limitation | Moved from the inventory to the 2011-2014 RMP. Start date: 2011/02; End date: 2014/02 |  | MS request | R4 | Agency | Decision | 2011 | 02 | 2014 | 02 | 0.15 | 0.15 | 0.08 | 0.075
2011-2014 | 27&29.029 | Rotorcraft AMC Revision | New task in cooperation with FAA (proposed on 12.05.2010) |  | FAA Harmonisation Certification request | R4 | Agency (FAA cooperation) | Decision | 2010 | 02 | 2013 | 01 | 0.15 | 0.1 | 0.03
2011-2014 | 31.003 | Free Gas Balloons Development of the Certification Specifications for Free Gas Balloons (CS-31GB) | Ending date changed from 2011.01 to 2011.02 | pre-RIA old format | Industry Request | R4 | Group | Decision | 2009 | 02 | 2011 | 02 | 0.025
2011-2014 | 31.004 | Tethered Gas Balloons Development of the Certification Specifications for Tethered Gas Balloons (CS-31TGB) | Ending date changed from 2011.01 to 2012.01 | pre-RIA old format | Industry Request | R4 | Group | Decision | 2009 | 02 | 2012 | 01 | 0.1 | 0.05
2011-2014 | 34.002 | Update CS 34 to refer to the Environmental Technical Manual on Emissions Certification as amended after CAEP 8. |  | B12 | ICAO alignment | R2 | Agency | Decision | 2010 | 04 | 2012 | 03 |  | 0.05
2011-2014 | 34.003 | Update CS 34 to refer to the Environmental Technical Manual on Emissions Certification as amended after CAEP/9. |  | pre-RIA will be provided in 2013 | ICAO alignment | R2 | Agency | Decision | 2013 | 04 | 2015 | 03
2011-2014 | 36.006 | Update CS 36 to refer to the Environmental Technical Manual on Noise Certification as amended after CAEP 8. |  | B12 | ICAO alignment | R2 | Agency | Decision | 2010 | 04 | 2012 | 03
2011-2014 | 36.007 | Update CS 36 to refer to the Environmental Technical Manual on Noise Certification as amended after CAEP/9. |  | pre-RIA will be provided in 2013 | ICAO alignment | R2 | Agency | Decision | 2013 | 04 | 2015 | 03
2011-2014 | 66.004 (b) | Time limit for demonstration of compliance with knowledge and experience requirements - AMC/GM 66.A.10 Most authorities feel that the period during which compliance with knowledge and experience requirements must be shown, should be limited. The objective of the task is to examine if and how the time a person may take to pass all the modules, should be limited. | Ending date changed from 2011.01 to 2011.02 | pre-RIA old format | MS Request Industry Request | R4 | Agency | Decision | 2005 | 03 | 2011 | 02 | 0.025
2011-2014 | 66.006 (b) | Privileges of B1 and B2 licenses: The objective is to provide for clarity as regards the privileges of B1 and B2 license holders for electrical/instrument systems. Envisaged deliverables: decisions amending AMC/GM to Part-145, Part-66 and Part-147 Depending on outcome of opinion on task 66.006 (a) in 2009 RMP. | Ending date changed from 2011.01 to 2011.02 | pre-RIA old format | MS Request Industry Request | R4 | Group | Decision | 2006 | 01 | 2011 | 02 | 0.15
2011-2014 | 66.007 | Question data bank Work was started by the JAA on a question databank. It will become the only source of questions and Appendix II will be modified to only require the use of the databank. |  | pre-RIA old format | MS Request | R4 | Agency | Decision | 2012 | 01 | 2013 | 01 |  | 0.075 | 0.05
2011-2014 | 66.009 (b) | Type and group ratings: The objective is to review experience requirements for the issue of group ratings for light aircraft, as well as the definition of simple and complex aircraft Envisaged deliverables: decisions amending AMC/GM to Part-66. Depending on outcome of opinion on task 66.009 (a) in 2009 RMP. | Ending date changed from 2011.01 to 2011.02 | pre-RIA old format | MS Request Industry Request | R4 | Group | Decision | 2006 | 02 | 2011 | 02 | 0.15
2011-2014 | 66.011 (b) | Type training: The objective is to harmonize practices and avoid unjustified differences in type training duration. Envisaged deliverables: decisions amending AMC/GM to Part-66. Depending on outcome of opinion on task 66.011 (a) in 2009 RMP. | Ending date changed from 2011.01 to 2011.02 | pre-RIA old format | MS Request Industry Request Safety related | R4 | Group | Decision | 2005 | 03 | 2011 | 02 | 0.15
2011-2014 | 66.022 (b) | License for non complex aircraft maintenance engineers Envisaged deliverable: A Decision amending AMC/GM to Part-145, Part-66 and Part-145 following their amendment as suggested here above. | Ending date changed from 2011.01 to 2011.02 | pre-RIA old format | Industry Request | R4 | Group | Decision | 2007 | 01 | 2011 | 02 | 0.15
2011-2014 | 66.025 | List of type ratings This task has for objective to regularly update this living AMC, which is used as a reference for issuing type ratings. Envisaged deliverable: A decision updating Appendix I of AMC to Part-66. |  | pre-RIA not required according to Art 3(5) of EASA MB Decision 08-2007 | MS Request | R4 | Agency | Decision | 2010 | 01 | 2011 | 01 | 0.075
2011-2014 | 66.026 | List of type ratings This task has for objective to regularly update this living AMC, which is used as a reference for issuing type ratings. Envisaged deliverable: A decision updating Appendix I of AMC to Part-66. |  | pre-RIA not required according to Art 3(5) of EASA MB Decision 08-2007 | MS Request | R4 | Agency | Decision | 2011 | 01 | 2012 | 01 | 0.1 | 0.05
2011-2014 | 66.027 (a) | Adapt the licence for avionics engineers to light aircrafts | New task | pre-RIA old format | Industry Request | R4 | Group | Opinion | 2010 | 01 | 2013 | 01 | 0.1 | 0.125 | 0.05
2011-2014 | 66.027 (b) | Creation of a license for avionics engineers | New task. Title changed to get rid of B4 (S) | pre-RIA old format | Industry Request | R4 | Group | Decision | 2010 | 03 | 2013 | 02 | 0.1 | 0.125 | 0.075
2011-2014 | ADR.001 (a) | Requirements for aerodrome operators and competent authorities (IRs) | New Task. Title changed after the consultation on the ToR (A, S). Starting date changed from 2010.02 to 2010.03 (I) | BR task - no pre-RIA required | Basic Regulation | R5 | Group | Opinion | 2010 | 03 | 2012 | 04 | 0.5 | 1.5
2011-2014 | ADR.001 (b) | Requirements for aerodrome operators and competent authorities (AMCs) | New Task. Title changed after the consultation on the ToR (A, S). Starting date changed from 2010.02 to 2010.03 (I) | BR task - no pre-RIA required | Basic Regulation | R5 | Group | Decision | 2010 | 03 | 2013 | 04 | 0.5 | 0.5 | 1.5
2011-2014 | ADR.002 (a) | Requirements on aerodrome operations (IRs) | New Task. Starting date changed from 2010.02 to 2010.03 (I) | BR task - no pre-RIA required | Basic Regulation | R5 | Group | Opinion | 2010 | 03 | 2012 | 04 | 0.5 | 1.5
2011-2014 | ADR.002 (b) | Requirements on aerodrome operations (AMCs) | New Task. Starting date changed from 2010.02 to 2010.03 (I) | BR task - no pre-RIA required | Basic Regulation | R5 | Group | Decision | 2010 | 03 | 2013 | 04 | 0.5 | 0.5 | 1.5
2011-2014 | ADR.003 (a) | Requirements on aerodrome design (IRs) | New Task. Starting date changed from 2010.02 to 2010.03 (I) | BR task - no pre-RIA required | Basic Regulation | R5 | Group | Opinion | 2010 | 03 | 2012 | 04 | 1 | 1.5
2011-2014 | ADR.003 (b) | Requirements on aerodrome design (CSs and AMCs) | New Task. Starting date changed from 2010.02 to 2010.03 (I) | BR task - no pre-RIA required | Basic Regulation | R5 | Group | Decision | 2010 | 03 | 2013 | 04 | 1 | 1.5 | 2
2011-2014 | ATM.001 (a) | Requirements on Air Navigation Service Provision | Ending date changed from 2011.04 to 2012.02 due to the allocation of resources to the fast-track task ATM.007. New starting date 2010.02 and ending date 2013.02 (I) | BR task - no pre-RIA required | Basic Regulation | R5 | Group | Opinion | 2010 | 02 | 2013 | 02 | 3 | 2 | 1
2011-2014 | ATM.001 (b) | Requirements on Air Navigation Service Provision (CS, AMC and GM) | Ending date changed from 2012.04 to 2013.04. New starting date 2010.02 and ending date 2014.04 (I) | BR task - no pre-RIA required | Basic Regulation | R5 | Group | Decision | 2010 | 02 | 2014 | 04 | 2.5 | 2.5 | 2 | 0.5
2011-2014 | ATM.002 (b) | Introduction of ACAS II software version 7.1 Update of AMC-20 | Starting date changed from 2009.04 to 2010.02 and ending date from 2011.04 to 2012.04 (I) |  | Air Accident Investigation recommend Safety related | R5 | Agency | Decision | 2010 | 02 | 2012 | 04 | 1 | 0.2
2011-2014 | ATM.003 (a) | Requirements on Air Traffic Controller licensing | Ending date changed from 2011.04 to 2012.02 due to the allocation of resources to the fast-track task ATM.008. New starting date 2010.02 and ending date 2013.04 (I) |  | Basic Regulation | R5 | Group | Opinion | 2010 | 02 | 2013 | 04 | 2 | 1 | 1
2011-2014 | ATM.003 (b) | Requirements on Air Traffic Controller licensing (AMC and GM) | Starting and ending date changed to align to ATM.003 (a) (I) |  | Basic Regulation | R5 | Group | Decision | 2010 | 02 | 2013 | 04 | 1.5 | 2.5 | 1
2011-2014 | ATM.004 (a) | Requirements on Competent Authorities in ATM/ANS | Ending date changed from 2011.04 to 2012.02 due to the allocation of resources to the fast-track task ATM.009. New ending date 2012.04 (I) | BR task - no pre-RIA required | Basic Regulation | R5 | Group | Opinion | 2009 | 04 | 2012 | 04 | 2 | 1.5
2011-2014 | ATM.004 (b) | Requirements on Competent Authorities in ATM/ANS (AMC and GM) |  | BR task - no pre-RIA required | Basic Regulation | R5 | Group | Decision | 2009 | 04 | 2012 | 04 | 1.5 | 2.5
2011-2014 | ATM.005 (a) | Requirements for systems and constituents |  | BR task - no pre-RIA required | Basic Regulation | R5 | Group | Opinion | 2011 | 02 | 2013 | 04 | 1 | 0.5 | 1.5
2011-2014 | ATM.005 (b) | Requirements for systems and constituents (CS, AMC and GM) |  | BR task - no pre-RIA required | Basic Regulation | R5 | Group | Decision | 2011 | 02 | 2014 | 01 | 1.5 | 1 | 1.5 | 1
2011-2014 | AWO.001 | Miscellaneous CS-AWO This task results from the JAA/FAA harmonization program and addresses: - High Altitude Landing System Performance (JAA NPA AWO-11) - Structural Limit Loads and Lateral Touchdown Performance (JAA NPA AWO-14) - Revisions to CS-AWO resulting from JAR/FAR 25.1329 activity (JAA NPA AWO-16) (linked to NPA 25F-344) - Incorporation of new technologies and replacement of existing Special Conditions: - Introduction of Head-Up Guidance Landing System (JAA NPA AWO-13) |  | B8 | Industry Request | R4 | Agency | Decision | 2011 | 01 | 2013 | 02 | 0.1 | 0.125 | 0.125
2011-2014 | AWO.002 | Automatic pilot super Fail-Passive criteria Clarification of requirements to resolve comments submitted by industry on CS-AWO during its initial consultation in 2003. | Starting date changed from 2004.03 to 2012.02 |  | Industry Request | R4 | Group | Decision | 2012 | 02 | 2014 | 02 |  | 0.075 | 0.15 | 0.05
2011-2014 | AWO.006 | GNSS Landing System (GLS): The objective of the task is to establish requirements for: - Category 1 Approach including autoland capability - GLS Signal-in-Space - GBAS (Ground Based Augmentation System) Failure Modes - Certification of GLS - Certification credit for ILS (Instrument Landing Systems) look-alike GLS - Combination ILS/MLS (Microwave Landing Systems)/GLS certification - SBAS (Space Based Augmentation Systems) |  | pre-RIA old format | Industry Request | R4 | Group | Decision | 2013 | 01 | 2014 | 02 |  |  | 0.15 | 0.1
2011-2014 | AWO.007 | New Technologies The objective of the task is to establish requirements for the certification of Enhanced Vision and Synthetic Vision Systems (EVS and SVS) |  | pre-RIA old format | Industry request | R4 | Group | Decision | 2013 | 04 | 2016 | 01 |  |  | 0.15 | 0.15
2011-2014 | BR.008 | Implementation of CAEP 8 amendments | Ending date 2011.04 (I) | B12 | ICAO alignment | R2 | Agency | Opinion | 2010 | 04 | 2011 | 04 | 0.3
2011-2014 | BR.010 | Adaption of BR for airworthiness of small aicraft GA |  | pre-RIA old format | Industry Request | R4 | Group | Opinion | 2010 | 03 | 2013 | 01 | 0.1 | 0.125 | 0.05
2011-2014 | BR.012 | Implementation of CAEP 9 amendments |  | pre-RIA will be provided in 2013 | ICAO alignment | R2 | Agency | Opinion | 2013 | 04 | 2014 | 04 |  |  | 0.1 | 0.3
2011-2014 | E.004 | Vibration Review of CS-E 650 (Vibration surveys) to consider problems encountered during recent certification activities | New starting date on 2011.02. Method changed (S) | pre-RIA old format | Certification request | R4 | Agency (using Industry Group) | Decision | 2011 | 02 | 2014 | 03 | 0.075 | 0.125 | 0.125 | 0.075
2011-2014 | E.009 | Ice Protection: This task aims to review the current knowledge base and certification experience relating to compliance with CSE 780 and to update the certification specification and AMC to reflect the state-of-art and current best practice | Ending date changed from 2011.01 to 2012.02 | pre-RIA old format | Safety related | R4 | Agency | Decision | 2008 | 03 | 2012 | 02 | 0.1 | 0.075
2011-2014 | E.010 | Initial Maintenance Inspection Consider the introduction within CS-E of a requirement based upon, if not identical to, the current FAR 33.90. This will ensure that engine tests are conducted at conditions representative of those expected to occur in service prior to the issue of a TC. | Starting date changed from 2013.02 to 2012.02 and ending date changed from 2015.03 to 2014.03 |  | Certification request | R4 | Agency | Decision | 2012 | 02 | 2014 | 03 |  | 0.05 | 0.15 | 0.1
2011-2014 | E.011 | Propulsion lubricating oil |  | pre-RIA old format | Industry Request | R4 | Agency | Decision | 2013 | 01 | 2014 | 01 |  |  | 0.165 | 0.1
2011-2014 | E.013 | Engine open rotor | Moved from the inventory to the 2011-2014 RMP. Start date: 2010/04; End date: 2013/01 |  | Industry request | R4 | Agency (using Industry Group) | Decision | 2010 | 04 | 2013 | 01 | 0.01 | 0.01 | 0.01
2011-2014 | E.014 | Engine core lock (linked with FAA/AIA initiative following an NTSB recommendation) |  | pre-RIA old format | Safety related | R4 | Agency | Decision | 2012 | 01 | 2014 | 01 |  | 0.075 | 0.15 | 0.05
2011-2014 | E.015 | Incorporation of special conditions in CS-E | Starting date changed from 2011.01 to 2012.02 and ending date changed from 2013.01 to 2014.01 | pre-RIA old format | Certification request | R4 | Agency | Decision | 2012 | 02 | 2014 | 01 |  | 0.05 | 0.15 | 0.075
2011-2014 | ETSO.007 | Systematic review and transposition of existing FAA TSO for parts and appliances into EASA ETSO |  | pre-RIA not required according to Art 3(5) of EASA MB Decision 08-2007 | Industry request Certification request | R4 | Agency | Decision | 2008 | 03 | 2011 | 01 | 0.075
2011-2014 | ETSO.008 | Systematic review and transposition of existing FAA TSO for parts and appliances into EASA ETSO | Starting date changed from 2009.04 to 2010.01 and ending date changed from 2011.03 to 2012.02 | B9 | Industry request Certification request | R4 | Agency | Decision | 2010 | 01 | 2012 | 02 | 0.1 | 0.05
2011-2014 | ETSO.011 | Systematic review and transposition of existing FAA TSO for parts and appliances into EASA ETSO | New task equivalent to ETSO.008 (I) |  | Industry request Certification request | R4 | Agency | Decision | 2011 | 01 | 2013 | 02 | 0.0276 | 0.1 | 0.05
2011-2014 | FCL.001 (a) | Implementing rules for pilot licensing The objective of this task is to produce, based on JAR-FCL 1, 2 and 3, JAR-STD and the input from the group MDM.032, the rules that are necessary for the implementation of the extended Basic Regulation. Envisaged deliverable: An opinion proposing a set of rules covering all pilot licenses. | Ending date changed from 2011.02 to 2011.01 |  | Basic Regulation | R3 | Group | Opinion | 2006 | 03 | 2011 | 01 | 1
2011-2014 | FCL.001 (b) | Implementing rules for pilot licensing Based on the outcome of task FCL.001(a), the envisaged deliverable: a decision for AMC/GM. | Title changed - Ending date changed from 2012.02 to 2012.01 |  | Basic Regulation | R3 | Group | Decision | 2006 | 03 | 2012 | 01 | 1.25 | 0.063
2011-2014 | FCL.002 (a) | Updating EASA FCL implementing rules | Title changed and method agreed as group - Starting date changed from 2011.02 to 2011.01 and ending date from 2014.02 to 2014.01 Title amended (S) | pre-RIA old format | Basic Regulation | R3 | Group | Opinion | 2011 | 01 | 2014 | 01 | 0.25 | 0.25 | 0.25 | 0.063
2011-2014 | FCL.002 (b) | Updating EASA FCL implementing rules First editorial review of the published AMC/GM, including transposition of the former JAA Learning Objectives for professional licences and the instrument rating, plus any other JAA material not introduced in task FCL.001. Separate rulemaking task for MED issues | Title changed and method agreed as group - Starting date changed from 2011.02 to 2011.01 and ending date from 2015.02 to 2015.01 | pre-RIA old format | Basic Regulation | R3 | Group | Decision | 2011 | 01 | 2015 | 01 | 0.125 | 0.125 | 0.125 | 0.125
2011-2014 | FCL.004 (a) | Requirements for cruise relief co-pilots. Review of the Implementing Rules for type ratings to address conflicts with the training and checking requirements for cruise relief co-pilots | Starting date changed from 2011.01 to 2012.02 and ending date from 2014.02 to 2015.02 | pre-RIA old format | Industry Request | R3 | Group | Opinion | 2012 | 02 | 2015 | 02 |  | 0.031 | 0.063 | 0.063
2011-2014 | FCL.004 (b) | Requirements for cruise relief co-pilots Review of the AMC/GM for type ratings to address conflicts with the training and checking requirements for cruise relief co-pilots | Starting date changed from 2011.02 to 2012.02 and ending date from 2015.02 to 2016.02 | pre-RIA old format | Industry Request | R3 | Group | Decision | 2012 | 02 | 2016 | 02 |  | 0.031 | 0.063 | 0.063
2011-2014 | FCL.006 (a) | Extension of competency-based training to all licences and ratings and extension of TEM principle to all licences and ratings (IRs) | Title changed - Moved from Inventory to the RMP 2011-2014 - Method defined and dates set up. | B18 | JAA Transfer | R3 | Group | Opinion | 2014 | 02 | 2017 | 02 |  |  |  | 0.125
2011-2014 | FCL.006 (b) | Extension of competency-based training to all licences and ratings and extension of TEM principle to all licences and ratings (AMC/GM) | Title changed - Moved from Inventory to the RMP 2011-2014 - Method defined and dates set up. | B18 | JAA Transfer | R3 | Group | Decision | 2014 | 02 | 2018 | 02 |  |  |  | 0.125
2011-2014 | FCL.007 (a) | Review of IR to assure alignment with the new ICAO doc. 9625, 3rd edition as a new technical basis for all international standards for new fidelity levels of Flight Simulation Training Devices (FSTDs) required to support each of the required training tasks | Title changed - Moved from Inventory to the RMP 2011-2014 - Method defined and dates set up. | B18 | ICAO alignment | R3 | Group | Opinion | 2012 | 03 | 2015 | 03 |  | 0.063 | 0.125 | 0.125
2011-2014 | FCL.007 (b) | Review of CS/AMC/GM to assure alignment with the new ICAO doc. 9625, 3rd edition as a new technical basis for all international standards for new fidelity levels of Flight Simulation Training Devices (FSTDs) required to support each of the required training tasks | Title changed - Moved from Inventory to the RMP 2011-2014 - Method defined and dates set up. | B18 | ICAO alignment | R3 | Group | Decision | 2012 | 03 | 2016 | 03 |  |  | 0.125 | 0.125
2011-2014 | FCL.008 (a) | Qualifications for flying in IMC Review of the transposed JAR-FCL requirements for the Instrument Rating in line with the wider scope of EASA compared to JARs. | Ending date changed from 2010.04 to 2011.04 |  | MS Request | R3 | Group | Opinion | 2008 | 04 | 2011 | 04 | 0.125
2011-2014 | FCL.008 (b) | Qualifications for flying in IMC Review of the transposed JAR-FCL requirements for the Instrument Rating in line with the wider scope of EASA compared to JARs. | Ending date changed from 2011.04 to 2012.04 |  | MS Request | R3 | Group | Decision | 2008 | 04 | 2012 | 04 | 0.125 | 0.125
2011-2014 | M.009 | Maintenance check flights | Method changed (S) | pre-RIA old format | MS Request Safety related | R4 | Group | Decision | 2010 | 02 | 2013 | 01 | 0.1 | 0.125 | 0.05
2011-2014 | M.012 | M.A.403 AMC/GM is needed on deferred rectification for defects on operational equipment in General Aviation for which no minimum equipment list is required. |  |  | MS Request Industry Request | R4 | Agency | Decision | 2013 | 01 | 2015 | 02 |  |  | 0.165 | 0.15
2011-2014 | M.014 (a) | Contracting of continuing airworthiness management activities: A lot of work has been put into TGL 34 by the JAA. It was transferred into Part-M. This leaflet defined how an operator could outsource some of the tasks related to managing the continuing airworthiness of the aircraft it operates. This could lead to an amendment to the rule. | Ending date changed from 2011.01 to 2012.01 - Title changed | pre-RIA old format | Industry Request | R4 | Group | Opinion | 2006 | 01 | 2012 | 01 | 0.1 | 0.05
2011-2014 | M.014 (b) | Contracting of continuing airworthiness management activities: A lot of work has been put into TGL 34 by the JAA. It was transferred into Part-M. This leaflet defined how an operator could outsource some of the tasks related to managing the continuing airworthiness of the aircraft it operates. This could lead to an amendment to the AMC/GM. | Ending date changed from 2012.02 to 2013.02 | pre-RIA old format | Industry Request | R4 | Group | Decision | 2006 | 01 | 2013 | 02 | 0.1 | 0.125 | 0.1
2011-2014 | M.022 | Amend AMC M.A.706(e) to cover additional cases for the competent authority to accept that the nominated post holder in the operator/Part-M Subpart G organisation be employed by the contracted Part-145 organisation There is no difference in responsibility, accountability and ability with regard to supervise and maintain continuous airworthiness between an AOC-holder with his own Part 145 organization integrated in the AOC organization to a system were the overall accountability for airworthiness and maintenance is held by two different organization and the same person is Accountable Manager in both organization is held by two different organization and the same person is Accountable Manager in both organization | Title changed | pre-RIA old format | MS Request | R4 | Agency | Decision | 2009 | 02 | 2012 | 01 | 0.1 | 0.05
2011-2014 | M.025 | Amendments (rule and AMC/GM) adapted to the process of granting foreign Subpart F and Subpart G approvals | Starting date changed from 2009.03 to 2010.03 and Ending date changed from 2011.02 to 2012.02 | pre-RIA old format | Certification request | R4 | Agency | Opinion | 2010 | 03 | 2012 | 02 | 0.1 | 0.075
2011-2014 | M.027 | Guidance Material related to the Aircraft Continuing Airworthiness Monitoring | Title changed | B9 | MS request | R4 | Agency | Decision | 2010 | 01 | 2012 | 01 | 0.1 | 0.05
2011-2014 | M.029 | Additional guidance on the CAMO responsibilities - More guidance on the CAMO responsibilities before the a/c takes off. Information needed: a.Final CRS b.Other things c.Tech log | New task. Moved from Inventory to RMP 2011-2014 (S) |  | Industry and MS request | R4 | Group | Decision | 2011 | 02 | 2014 | 01 | 0.025 | 0.075 | 0.075 | 0.025
2011-2014 | MDM.003 (b) | Flight testing Envisaged deliverable: a decision amending AMC/GM to Part 21 M (subject to amendment of Part 21 in accordance with MDM.003(a)). | Task started and ending date changed from 2013.01 to 2012.02 |  | Industry Request | R4 | Group | Decision | 2004 | 04 | 2012 | 02 | 0.075 | 0.075
2011-2014 | MDM.003 (c) | A-NPA on Flight test Engineer (FTE) Licensing Discuss the creation of a license (licensing scheme) for FTE that are assigned for duties in an aircraft for the purpose of conducting flight tests or assisting the pilot in the operation of the aircraft and its systems during flight test activities. The A-NPA will discuss the benefits, issues and where to place possible requirements for such a license. | New Task carried out by the Agency with inputs from the review group (I) | pre-RIA are not envisaged for A-NPA by article 14 of the MB procedures | Industry Request | R4 | Agency | Decision | 2011 | 01 | 2011 | 04 | 0.075
2011-2014 | MDM.020 | Definition of “critical systems” This notion was introduced through the human factor requirements in Part-145. It is necessary to develop AMC/GM material in order to explain the concept. |  | pre-RIA old Format | Safety related | R4 | Group | Opinion | 2009 | 01 | 2012 | 01 | 0.1 | 0.05
2011-2014 | MDM.024 | HIRF (High Intensity Radiated Fields) Harmonization activity on a new CS/FAR xx.1317 and associated AC/AMC, on protection from HIRF. For CS-23, -25, -27 and -29 | Moved from the Inventory to RMP 2011-2014 (I) | pre-RIA old format | Safety related | R4 | Agency (FAA cooperation) | Decision | 2011 |  | 2013 | 01 | 0.01 | 0.015 | 0.005
2011-2014 | MDM.028 (a) | Development of an Ageing Aircraft Structure plan: This plan will provide a regulatory framework taking into account actions already included in this programme and will consider extension to other aircraft than large aeroplanes. Task MDM.028 (a) is the development of the technical elements for the large aeroplanes plan adding requirements for the existing fleet and modification to CS 25. | The task will end both in an Opinion and a Decision. Ending date changed from 2011.01 to 2012.01. However the task will also deliver a Decision to CS 25 in 2011.02 (title changed as consequence) | pre-RIA old format | Safety related | R4 | Group | Opinion | 2007 | 02 | 2012 | 01 | 0.1 | 0.05
2011-2014 | MDM.028 (b) | Development of an Ageing Aircraft Structure plan: - Develop a Regulatory Impact Assessment (RIA) for identifying the need to go beyond large aeroplanes - Based on the results of the RIA, develop comparable technical elements for a plan in a comparable manner as for task (a). - Review and develop AMC 20-20, to reflect its wider applicability, as necessary | The task will end both in an Opinion and a Decision. Starting date changed from 2012.01 to 2011.03 | pre-RIA old format | Safety related | R4 | Group | Opinion | 2011 | 03 | 2014 | 02 | 0.025 | 0.15 | 0.15 | 0.07
2011-2014 | MDM.028 (c) | Development of an Ageing Aircraft Structure plan: Change of Operational Use: this is not strictly only an ageing aircraft issue, but is related. - Amend xx.1529 to add a requirement on the TCH to publish key assumptions used in the structural analysis. - Propose compatible changes to Part M as necessary to ensure operators observe these assumptions. | The task will end both in an Opinion and a Decision | pre-RIA old format | Safety related | R4 | Group | Opinion | 2012 | 01 | 2014 | 02 |  | 0.075 | 0.15 | 0.05
2011-2014 | MDM.030 (a) | UAS further regulation Development of IR for the operations of UAS. |  |  | Basic Regulation | R3 | Group | Opinion | 2012 | 01 | 2014 | 02 |  | 0.25 | 0.25 | 0.25
2011-2014 | MDM.030 (a) | UAS further regulation Development of IR for the operations of UAS. |  |  | Legal obligation MS Request | R4 | Group | Opinion | 2012 | 01 | 2014 | 02 |  | 0.075 | 0.15 | 0.12
2011-2014 | MDM.030 (b) | UAS further regulation Development of AMC/GM for the operations of UAS. | Starting date 2012.03 and ending date 2016.03 |  | Basic Regulation | R3 | Group | Decision | 2012 | 03 | 2016 | 03 |  | 0.25 | 0.25 | 0.25
2011-2014 | MDM.030 (b) | UAS further regulation Development of AMC/GM for the operations of UAS. |  |  | Legal obligation MS Request | R4 | Group | Decision | 2014 | 01 | 2014 | 03 |  |  |  | 0.125
2011-2014 | MDM.030 (c) | UAS further regulation Development of specific CS for UAS airworthiness |  |  | Legal obligation | R4 | Group | Decision | 2014 | 01 | 2016 | 03 |  |  |  | 0.125
2011-2014 | MDM.031 (a) | Commercial Air transportation aeroplane operations Single Engine IMC Development of the Implementing Rules for the airworthiness and operational approval. | Starting date changed from 2013.01 to 2012.01 and ending date changed from 2016.01 to 2015.01 |  | ICAO alignment | R3 | Group | Opinion | 2012 | 01 | 2015 | 01 |  | 0.125 | 0.125 | 0.125
2011-2014 | MDM.031 (b) | Commercial Air transportation aeroplane operations Single Engine IMC Development of the guidance material for the airworthiness and operational approval. | Starting date changed from 2013.01 to 2012.01 and ending date changed from 2017.01 to 2016.01 |  | ICAO alignment | R3 | Group | Decision | 2012 | 01 | 2016 | 01 |  | 0.125 | 0.125 | 0.125
2011-2014 | MDM.032 (d) | Regulation of aircraft other than complex motor powered aircraft, used in non-commercial activities: Envisaged deliverable: a Decision amending AMC/GM to Part 21. Depending on outcome of Opinion on task MDM.032 (e). |  | pre-RIA old format | Industry Request | R4 | Agency | Decision | 2006 | 01 | 2013 | 01 | 0.1 | 0.15 | 0.075
2011-2014 | MDM.038 | Non binding guidance on TBO limits The Agency is facing a situation where the NAAs have different procedures to control the TBO of piston engines operated in their countries which do not refer systematically to the manufacturer’s instructions, and a request has been raised to Rulemaking to launch a task to issue guidance to the NAAs on this question. | Ending date changed from 2011.01 to 2011.02. And then to 2012.01 (I) | pre-RIA old format | MS Request | R4 | Agency | Decision | 2009 | 02 | 2012 | 01 | 0.05 | 0.05
2011-2014 | MDM.042 | The Identification of existing defences in maintenance processes to detect major configuration differences Review applicable airworthiness regulations and standards, as well as aircraft, engines and component maintenance manuals, to ensure that adequate defences exist in the preinstallation, maintenance planning process to detect major configuration differences and to establish the required support resources for technicians responsible for the work. |  |  | Safety related | R4 | Group | Opinion | 2012 | 04 | 2015 | 01 |  | 0.075 | 0.15 | 0.15
2011-2014 | MDM.047 | Alignment of Regulation No (EC) 2042/2003 with Regulation (EC) No 216/2008 and with ICAO Annex 6 requirement for human factor principles to be observed in the design and application of the aircraft maintenance programme | Title cahnged - Starting date changed from 2009.01 to 2010.02 |  | Legal obligation | R4 | Agency | Opinion | 2010 | 02 | 2011 | 02 | 0.025
2011-2014 | MDM.048 | Issue certification specifications for standard changes and repairs based on FAA AC 43-13 Rule and guidance should be developed on acceptable methods, techniques and practices on aircraft modifications (AC43-13). | Ending date changed from 2013.01 to 2013.02 | pre-RIA old format + B9 according to pre-RIA in the new format | Industry Request | R4 | Group | Decision | 2011 | 01 | 2013 | 02 | 0.1 | 0.125 | 0.1
2011-2014 | MDM.054 | De-Icing - anti icing / AMC and GM following A.NPA 2007-13 |  | pre-RIA old format | Safety Related | R4 | Agency | Decision | 2009 | 01 | 2011 | 01 | 0.025
2011-2014 | MDM.055 | New structure for Regulation 2042 and SMS embodiment | Starting date changed from 2009.01 to 2010.03 and ending date changed from 2012.01 to 2012.03 | B12 | MS Request | R4 | Agency | Opinion | 2010 | 03 | 2012 | 03 | 0.1 | 0.125
2011-2014 | MDM.056 | Instructions for continuing airworthiness | Ending date changed from 2012.01 to 2013.01 | pre-RIA old format | MS Request | R4 | Group | Opinion | 2009 | 02 | 2013 | 01 | 0.1 | 0.125 | 0.075
2011-2014 | MDM.057 | Miscelaneous of Parts M |  | pre-RIA old format | MS Request | R4 | Agency | Decision | 2013 | 01 | 2015 | 02 |  |  | 0.125 | 0.15
2011-2014 | MDM.058 | Miscelaneous of Parts 145 |  | pre-RIA old format | MS Request | R4 | Agency | Decision | 2013 | 01 | 2016 | 01 |  |  | 0.165 | 0.15
2011-2014 | MDM.059 | Miscelaneous of Parts 66, 147 |  | pre-RIA old format | MS Request | R4 | Agency | Decision | 2013 | 01 | 2016 | 01 |  |  | 0.125 | 0.15
2011-2014 | MDM.060 | New structure for Regulation 1702 and SMS embodiment | Title changed | B12 | MS Request | R4 | Agency | Opinion | 2010 | 03 | 2013 | 01 | 0.1 | 0.125 | 0.05
2011-2014 | MDM.061 | S & CEH Certif Memos publication: new generic GM (applicable to all CS) |  | pre-RIA old format | Certification request | R4 | Agency | Decision | 2011 | 04 | 2013 | 03 | 0.025 | 0.125 | 0.075
2011-2014 | MDM.062 (a) former OPS.013 (a) | RNP Operations in areas other than European Airspace Development of Implementing Rules for the RNP approval. | Title changed | pre-RIA old format | Tecnological Development | R3 | Group | Opinion | 2012 | 01 | 2015 | 01 |  | 0.125 | 0.125 | 0.125
2011-2014 | MDM.062 (b) former OPS.013 (b) | RNP Operations in areas other than European Airspace Development of AMC/GM for the RNP approval. | Title changed | pre-RIA old format | Tecnological Development | R3 | Group | Decision | 2012 | 01 | 2016 | 01 |  | 0.125 | 0.125 | 0.125
2011-2014 | MDM.063 (a) former OPS.029 (a) | Child restraint devices Development of Implementing Rules based on the results of the study on Child Restraint Systems (CRS). | Starting date changed from 2011.02 to 2011.04 and ending date from 2014.02 to 2014.04 | Study implemented | EP Request | R3 | Group | Opinion | 2011 | 04 | 2014 | 04 | 0.031 | 0.125 | 0.125 | 0.125
2011-2014 | MDM.063 (b) former OPS.029 (b) | Child restraint devices Development of AMC/GM based on the results of the study on Child Restraint Systems (CRS). | Starting date changed from 2011.02 to 2011.04 and ending date from 2015.02 to 2015.04 | Study implemented | EP Request | R3 | Group | Decision | 2011 | 04 | 2015 | 04 | 0.031 | 0.125 | 0.125 | 0.125
2011-2014 | MDM.064 (a) former OPS.066 (a) | Operations, training and equipment for high performance aircraft Review of Implementing Rules in relation to the operation of high performance aircraft. | Starting date changed from 2011.02 to 2012.02 and ending date from 2014.02 to 2015.02. Title amended (S) |  | Basic Regulation | R3 | Group | Opinion | 2012 | 02 | 2015 | 02 |  | 0.063 | 0.125 | 0.125
2011-2014 | MDM.064 (b) former OPS.066 (b) | Operations, training and equipment for high performance aircraft Review of Implementing Rules in relation to the operation of high performance aircraft. | Starting date changed from 2011.02 to 2012.02 and ending date from 2015.02 to 2016.02. Title amended (S) |  | Basic Regulation | R3 | Group | Decision | 2012 | 02 | 2016 | 02 |  | 0.063 | 0.125 | 0.125
2011-2014 | MDM.070 (a) (former FCL.003/ OPS.017) | Powered Lift (Tilt rotor) pilot licensing and operations Review of Implementing Rules for pilot licensing and operations in relation to the experience gained in the BA609 certification process | Method defined (Group) - Starting date changed from 2011.02 to 2012.02 and ending date from 2014.02 to 2015.02 |  | Basic Regulation | R3 | Group | Opinion | 2012 | 02 | 2015 | 02 |  | 0.063 | 0.125 | 0.125
2011-2014 | MDM.070 (b) (former FCL.003/ OPS.017) | Powered Lift (Tilt rotor) pilot licensing and operations Review of AMC/GM for pilot licensing and operations in relation to the experience gained in the BA609 certification process | Method defined (Group) - Starting date changed from 2011.02 to 2012.02 and ending date from 2014.02 to 2016.02 |  | Basic Regulation | R3 | Group | Decision | 2012 | 02 | 2016 | 02 |  | 0.063 | 0.125 | 0.125
2011-2014 | MDM.071 | Halon – Up-date of CSs, development of Guidance Material in order to comply with Regulation (EC) 1005/2009 and ICAO resolution. The ICAO resolution is still a draft (reference 33/1 “halon replacement”). The task will cover: - CS 25 up-date in order to align with (EC) Regulation and prescribe the minimum standards for the fire extinguishing agents - CS 26 (or IR) up-date in order to cover the production cut-off dates as mandated by ICAO - Guidance Material (AMC) to manufacturers and maintenance organizations to allow verification of the quality of halon in their possession through testing and internal procedures. The task may be split depending on the progress of each subtask. | New task. Task moved from inventory to RMP 2011-2014. Title changed (I) |  | Basic Regulation | R4 | Agency | Decision | 2011 | 01 | 2012 | 03 | 0.075 | 0.15
2011-2014 | MDM.072 (a) | Carriage of Special Categories of Passengers Review of the operational and certification requirements (IRs) relating to carriage of special categories of passengers based on the latest scientific research and associated recommendations | New task | B27 | Safety related | R3 | Group | Opinion | 2012 | 03 | 2015 | 03 |  | 0.063 | 0.125 | 0.125
2011-2014 | MDM.072 (b) | Carriage of Special Categories of Passengers Review of the operational and certification requirements (CS/AMC/GM) relating to carriage of special categories of passengers based on the latest scientific research and associated recommendations | New task | B27 | Safety related | R3 | Group | Decision | 2012 | 03 | 2016 | 03 |  | 0.063 | 0.125 | 0.125
2011-2014 | MDM.075 | Specialised tasks - There are a number of tasks which are performed independently of the aircraft type and for which an organisation approval is not available. Similarly to D1 (NDT) it could be also considered painting, weighing, welding, composite repairs | New task. Moved from the Inventory to the RMP 2011-2014 (I) |  | Industry request | R4 | Agency | Decision | 2011 | 02 | 2014 | 01 | 0.05 | 0.075 | 0.075 | 0.025
2011-2014 | MDM.076 | Technical records (M.A.305, 145.A.55), back to birth concept, components traceability, use of RFDS | New task. Task moved from Inventory to RMP 2011-2014 with 2011 as starting date (S) |  | Industry and MS request | R4 | Group | Decision | 2011 | 02 | 2014 | 02 | 0.05 | 0.075 | 0.075 | 0.05
2011-2014 | MDM.078 | Importing of aircraft from other regulatory system - Importing of aircraft into the "2042/2003" system from other regulatory systems (Foreign, national, military) | New task (including previous M.028). Moved from the Inventory to the RMP 2011-2014 (I + S) |  | Industry and MS request | R4 | Group | Opinion | 2011 | 02 | 2014 | 02 | 0.05 | 0.075 | 0.075 | 0.05
2011-2014 | MDM.082 | New training / Teaching technologies - 1) Introduction of: # Elearning and Edistance learning (level, content, nature of training, tools, instructor or Etutor, examination, forum of chat between tutors ans students, ATA chapter concerned, attestation, interactive concept etc); # Simulation devices or STDs (level, content, theoritical and practical tasks, assessment, etc; # Specialized training such as Human factors, FTS, continuation training etc (at least ensure consistency with existing literature and FCL...) 2) Recommendation for the use of blended teaching methods 3) Potential impacts for the duration of the training (Type rating training, basic knowledge etc) | New task. Moved from inventory to the RMP 2011-2014 (I) |  | Industry request | R4 | Group | Opinion | 2011 | 01 | 2014 | 01 | 0.075 | 0.075 | 0.075 | 0.025
2011-2014 | MDM.083 | Aligment with 21.039 (i) - Development of a type rating course by the part-147 organisation and approval by the Competent authority | New task. Moved from the Inventory to the RMP 2011-2014 (I) |  | Industry request | R4 | Group | Opinion | 2011 | 02 | 2014 | 02 | 0.025 | 0.075 | 0.05 | 0.05
2011-2014 | MDM.085 (a) former OPS.009 (a) | Runway Incursions Development of Operations Implementing Rules from transferred JAA tasks, including coordination with Aerodrome rulemaking | Task re-numbered - Starting date changed from 2012.01 to 2011.03 and ending date from 2015.01 to 2014.03. Task descriptiop amended (I) | pre-RIA old format | Safety related | R3 | Group | Opinion | 2011 | 03 | 2014 | 03 | 0.063 | 0.125 | 0.125 | 0.063
2011-2014 | MDM.085 (b) former OPS.009 (b) | Runway Incursions Development of Operations AMC/GM from transferred JAA tasks, including coordination with Aerodrome rulemaking | Task renumbered - Starting date changed from 2012.01 to 2011.03 and ending date from 2016.01 to 2015.03. Task descriptiop amended (I) | pre-RIA old format | Safety related | R3 | Group | Decision | 2011 | 03 | 2015 | 03 | 0.063 | 0.125 | 0.125 | 0.125
2011-2014 | MDM.089 | Certification Specifications for Aircraft and Engines/ International Volcanic Ash Task Force (IVATF) | New task related to volcanic ash issue (I) |  | EC request Safety related | R4 | Agency | Decision | 2010 | 03 | 2015 | 02 | 0.01 | 0.015 | 0.015 | 0.015
2011-2014 | MED.001 (a) | Updating EASA FCL Medical implementing rules First editorial review of the published IR, plus any other JAA material not introduced in task FCL.001 | New task |  | Basic Regulation | R3 | Group | Opinion | 2011 | 02 | 2014 | 02 | 0.094 | 0.125 | 0.125 | 0.063
2011-2014 | MED.001 (b) | Updating EASA FCL Medical implementing rules First editorial review of the published AMC/GM, plus any other JAA material not introduced in task FCL.001 | New task |  | Basic Regulation | R3 | Group | Decision | 2011 | 02 | 2015 | 02 | 0.094 | 0.125 | 0.125 | 0.125
2011-2014 | OPS.001 (a) | Implementing rules for air operations The objective of this task is to produce, based on JAR-OPS 0,1,2,3 and 4, “EU-OPS” and the input from the group MDM.032, the rules that are necessary for the implementation of the extended Basic Regulation. Envisaged deliverable: An opinion proposing a set of rules covering all aspects of air operations. |  |  | Basic Regulation | R3 | Group | Opinion | 2006 | 01 | 2011 | 02 | 1.75
2011-2014 | OPS.001 (b) | Implementing rules for air operations Based on the outcome of task OPS.001(a), the envisaged deliverable: a decision for AMC/GMs. |  |  | Basic Regulation | R3 | Group | Decision | 2006 | 01 | 2012 | 02 | 1.5 | 0.125
2011-2014 | OPS.004 (a) | Implementing rules for the oversight of third country aircraft The objective of this task is to produce, based on the SAFA Directive, the black list Directive and ICAO work in the field, the rules that are necessary for the implementation of the extended Basic Regulation. Envisaged deliverable: An opinion proposing a set of rules covering the oversight of third country aircraft and operators when in the territory covered by the Treaty. | Ending date changed from 2011.02 to 2011.04 |  | Basic Regulation | R3 | Agency | Opinion | 2006 | 04 | 2011 | 04 | 0.125
2011-2014 | OPS.004 (b) | Implementing rules for the regulation of third country aircraft Based on the outcome of task OPS.004(a), the envisaged deliverable: a decision for AMC/GMs. | Ending date changed from 2012.02 to 2012.04 |  | Basic Regulation | R3 | Agency | Decision | 2006 | 04 | 2012 | 04 | 0.125 | 0.125
2011-2014 | OPS.005 (a) | Updating EASA OPS implementing rules First editorial review of the published IR |  | pre-RIA old format | Basic Regulation | R3 | Agency | Opinion | 2013 | 03 | 2016 | 03 |  |  | 0.063 | 0.125
2011-2014 | OPS.005 (b) | Updating EASA OPS implementing rules First editorial review of the published AMC/GM |  | pre-RIA old format | Basic Regulation | R3 | Agency | Decision | 2013 | 03 | 2017 | 03 |  |  | 0.063 | 0.125
2011-2014 | OPS.016 (a) | Operations with Airships Development of Implementing Rules for the operation of airships. | Starting date changed from 2011.01 to 2014.02 and ending date from 2014.02 to 2017.02 |  | Basic Regulation | R3 | Group | Opinion | 2014 | 02 | 2017 | 02 |  |  |  | 0.125
2011-2014 | OPS.016 (b) | Operations with Airships Development of AMC/GM for the operation of airships. | Starting date changed from 2011.02 to 2014.02 and ending date from 2015.02 to 2018.02 |  | Basic Regulation | R3 | Group | Decision | 2014 | 02 | 2018 | 02 |  |  |  | 0.125
2011-2014 | OPS.055 (a) | FTL requirements for CAT aeroplane |  |  | Basic Regulation | R3 | Group | Opinion | 2009 | 02 | 2011 | 03 | 0.188
2011-2014 | OPS.055 (b) | FTL requirements for CAT aeroplane |  |  | Basic Regulation | R3 | Group | Decision | 2009 | 02 | 2012 | 02 | 0.25 | 0.188
2011-2014 | OPS.071 | CS-FTL Development of various CS-FTL for CAT with other than aeroplanes i.e. helicopters, airships and balloons, 'aerial work' activities and non-commercial operation of complex motor-powered aircraft. | Starting date changed from 2011.02 to 2012.02 and ending date from 2014.02 to 2017.02 |  | Basic Regulation | R3 |  | Decision | 2012 | 02 | 2017 | 02 |  | 0.5 | 0.5 | 0.5
2011-2014 | OPS.073 (a) | Operational requirements for manufacturer flights Development of Implementing rules for flights operated by manufacturers | Title changed - Starting date changed from 2011.02 to 2013.01 and ending date from 2014.02 to 2016.01. Change in task description (S) |  | Basic Regulation | R3 | Group | Opinion | 2013 | 01 | 2016 | 01 |  |  | 0.125 | 0.125
2011-2014 | OPS.073 (b) | Operational requirements for manufacturer flights Development of AMC/GM for flights operated by manufacturers | Title changed - Starting date changed from 2011.02 to 2013.01 and ending date from 2015.02 to 2017.01. Change in task description (S) |  | Basic Regulation | R3 | Group | Decision | 2013 | 02 | 2017 | 02 |  |  | 0.125 | 0.125
2011-2014 | OPS.074 (a) | Helicopter Vibration Health Monitoring: Additional Airworthiness IRs |  | A7 | JAA Transfer | R3 | Group | Opinion | 2013 | 03 | 2016 | 03 |  |  | 0.063 | 0.125
2011-2014 | OPS.074 (b) | Helicopter Vibration Health Monitoring: Additional Airworthiness AMC/GM/CS |  | A7 | JAA Transfer | R3 | Group | Decision | 2013 | 03 | 2017 | 03 |  |  | 0.063 | 0.125
2011-2014 | VLA.003 | Spin approval CS-VLA limited today to Normal Operations only. It is envisaged to add requirements for spin approval |  | pre-RIA old format | Industry Request | R4 | Group | Decision | 2012 | 03 | 2014 | 01 |  | 0.075 | 0.15 | 0.05
2011-2014 | VLA.008 | Incorporation of special conditions in CS-VLA Includes now Night VFR (VLA.001) Includes now Increas of MTOW to 890Kg (VLA.005) Include Towing. Updating of requirements for Glider towing, development of requirements for tow cable retraction systems (VLA.006) |  | pre-RIA old format | Certification request | R4 | Agency | Decision | 2011 | 01 | 2013 | 03 | 0.1 | 0.125 | 0.075
Note on N80: mianoma: FTE shared with 36.006 and BR.008
Note on N82: mianoma: FTE shared with 34.002 and BR.008
Note on O80: mianoma: FTE shared with 36.006 and BR.008
Note on O82: mianoma: see 34.002
Note on P81: mianoma: FTE shared with BR.012
Note on P83: mianoma: FTE shared with BR.012
Note on Q81: mianoma: FTE shared with BR.012
Note on Q83: mianoma: FTE shared with BR.012

## Inventory
Current rulemaking program | Task No. | Title | Changes from RMP 2010-2013 to RMP 2011-2014 (including consultation) | Pre-RIA score | Driver | R2 Environmental Protection R3 Flight Standards R4 Product Safety R5 ATM/Airport | Work method | Task leading to
inv. | 36.003 | Noise requirements for tilt-rotor aircraft Consider noise certification requirements for tilt-rotor aircraft based on guidelines in Attachment F to ICAO Annex 16, Volume I. Note would also need a revision to 21A.18(a). |  |  | ICAO alignment | R2 | Agency
inv. | MDM.037 | Preparation of amendments as needed after possible revision of Essential Requirements for Environmental Protection Such amendments may include changes to Part-21, CS-34 and CS-36 as appropriate |  |  |  | R2 | Agency
inv. | FCL.005 (a) | NPA on "Non-technical skills assessment system" for JAR-FCL 1 and 2 Transfer of JAA NPA-FCL 27 in the IR. |  |  | JAA Transfer | R3 |  | Opinion
inv. | FCL.005 (b) | NPA on "Non-technical skills assessment system" for JAR-FCL 1 and 2 Transfer of JAA NPA-FCL 27 in AMC/GM. |  |  | JAA Transfer | R3 |  | Decision
inv. | FCL.009 (a) | Training for flying by sole reference to standby instruments Development of IR addressing safety recommendation UNKG-2007-062. |  | B7 | Air Accident Investigation recommendation | R3 | Group | Opinion
inv. | FCL.009 (b) | Training for flying by sole reference to standby instruments Development of AMC/GM addressing safety recommendation UNKG-2007-062. |  | B7 | Air Accident Investigation recommendation | R3 | Group | Decision
inv. | FCL.010 | CQB CPL & ATPL A & H AMC | New task |  | JAA Transfer | R3 |  | Decision
inv. | FCL.011 | CQB LPL & PPL for aircraft other than A & H AMC | New task |  | Basic Regulation | R3 |  | Decision
inv. | FCL.012 (a) former OPS.020 (a) | Practical hypoxia training Development of IR addressing safety recommendation GREC-2006-044 following Helios B737 accident. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Opinion
inv. | FCL.012 (b) former OPS.020 (b) | Practical hypoxia training Development of AMC/GM addressing safety recommendation GREC-2006-044 following Helios B737 accident. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Decision
inv. | MDM.045 | Helicopter limited icing operations Transfer of JAA NPA-OPS 50 into AMC/GM. |  | pre-RIA old format | Industry Request | R3 |  | Decision
inv. | MDM.046 (a) | TGL 41 - Passive and Active RFID Devices (IRs) Task transferred from JAA and requested by the subSSCC | Title and scope changed for including "Active RFID Devices" | pre-RIA old format | JAA Transfer; subSSCC request | R3 |  | Opinion
inv. | MDM.046 (b) | TGL 41 - Passive and Active RFID Devices (AMC/GM) Task transferred from JAA and requested by the subSSCC | Title and scope changed for including "Active RFID Devices" | pre-RIA old format | JAA Transfer; subSSCC request | R3 |  | Decision
inv. | MDM.049 (a) | Standards and implementation of collision warning systems in the field of general aviation due to increasing number of near misses and mid air collisions Development of IR addressing safety recommendation. | Task to be performed in cooperation with ATM/Aerodromes Department |  | Air Accident Investigation recommendation | R3 |  | Opinion
inv. | MDM.049 (b) | Standards and implementation of collision warning systems in the field of general aviation due to increasing number of near misses and mid air collisions Development of AMC/GM addressing safety recommendation. | Task to be performed in cooperation with ATM/Aerodromes Department |  | Air Accident Investigation recommendation | R3 |  | Decision
inv. | MDM.051 | CVR Recording Quality Development of AMC/GM addressing safety recommendation. |  |  | Air Accident Investigation recommendation | R3 |  | Decision
inv. | MDM.053 (a) | Excursions through the HV diagram for CS-29 rotorcraft Review CS-29 and consider producing Supplement to the TC basis & review HFM for in-service helicopters in light of the Appendix 1 to JAR-OPS 3.005(c) alleviation | Moved to the inventory from the RMP 2010-2013 | B14 | Basic Regulation | R3 | Group | Opinion
inv. | MDM.053 (b) | Excursions through the HV diagram for CS-29 rotorcraft Review CS-29 and consider producing Supplement to the TC basis & review HFM for in-service helicopters in light of the Appendix 1 to JAR-OPS 3.005(c) alleviation | Moved to the inventory from the RMP 2010-2013 | B14 | Basic Regulation | R3 | Group | Decision
inv. | MDM.065 (a) | Authorisation of Aerodromes Rescue and Fire Fighting Services (RFFS) Transfer of JAA OPSG ongoing task in the IR. |  |  | JAA Transfer | R3 |  | Opinion
inv. | MDM.065 (b) | Authorisation of Aerodromes Rescue and Fire Fighting Services (RFFS) Transfer of JAA OPSG ongoing task in the AMC/GM. |  |  | JAA Transfer | R3 |  | Decision
inv. | MDM.073 (a) | Recorders for small aircraft Review of the operational and certification requirements (IRs) for recorders for small aircraft | New task | B8 | Air Accident Investigation recommendation | R3 | Group | Opinion
inv. | MDM.073 (b) | Recorders for small aircraft Review of the operational and certification requirements (CS/AMC/GM) for recorders for small aircraft | New task | B8 | Air Accident Investigation recommendation | R3 | Group | Decision
inv. | MDM.086 former OPS.068 | AMC/GM for small organisations Review of the AMC/GM in Part-OR to provide more detailed information to small organisations, e.g. a template for operations manuals. | New task |  | Basic Regulation | R3 | Group | Decision
inv. | MDM.087 (a) former OPS.035(a) | Feasibility of crash protected image recorders on the flight deck Development of IR addressing safety recommendation GREC-2006-48 following Helios B737 accident. | New task | B7 | Air Accident Investigation recommendation | R3 | Group | Opinion
inv. | MDM.087 (b) former OPS.035 (b) | Feasibility of crash protected image recorders on the flight deck Development of AMC/GM addressing safety recommendation GREC-2006-48 following Helios B737 accident. | New task | B7 | Air Accident Investigation recommendation | R3 | Group | Decision
inv. | MDM.088 (a) | Active RFID Devices (IRs) | New task related to MDM.046 |  | Flight Standards sub-SSCC | R3 |  | Opinion
inv. | MDM.088 (b) | Active RFID Devices (AMC/GM) | New task related to MDM.046 |  | Flight Standards sub-SSCC | R3 |  | Opinion
inv. | OPS.007 (a) | Data Link Recording Retrofit for aircraft used in CAT Transposition of JAA NPA-OPS 48A into IR. |  | pre-RIA old format | ICAO alignment | R3 |  | Opinion
inv. | OPS.007 (b) | Data Link Recording Retrofit for aircraft used in CAT Transposition of JAA NPA-OPS 48A into AMC/GM. |  | pre-RIA old format | ICAO alignment | R3 |  | Decision
inv. | OPS.008 (a) | Review and harmonisation with FAA of Aeroplane Performance for CAT Development of IR. |  | pre-RIA old format | FAA harmonisation | R3 |  | Opinion
inv. | OPS.008 (b) | Review and harmonisation with FAA of Aeroplane Performance for CAT Development of AMC/GM. |  | pre-RIA old format | FAA harmonisation | R3 |  | Decision
inv. | OPS.012 (a) | Unexpected Runway Changes Transferred task from the JAA OPSG. | Moved to the Inventory for a new allocation in the next months |  | Industry Request | R3 |  | Opinion
inv. | OPS.012 (b) | Unexpected Runway Changes Transferred task from the JAA OPSG. | Moved to the Inventory for a new allocation in the next months |  | Industry Request | R3 |  | Decision
inv. | OPS.018 (a) | Concurrent operation of helicopters and aeroplanes Review of IR relating to the operational restrictions to operate more than one type each for commercial air transport purposes. |  | pre-RIA old format | JAA Transfer | R3 |  | Opinion
inv. | OPS.018 (b) | Concurrent operation of helicopters and aeroplanes Review of AMC/GM relating to the operational restrictions to operate more than one type each for commercial air transport purposes. |  | pre-RIA old format | JAA Transfer | R3 |  | Decision
inv. | OPS.019 (a) | GNSS approaches with helicopters Development of IR to address new technological development. |  | pre-RIA old format | Tecnological Development | R3 |  | Opinion
inv. | OPS.019 (b) | GNSS approaches with helicopters Development of AMC/GM to address new technological development. |  | pre-RIA old format | Tecnological Development | R3 |  | Decision
inv. | OPS.023 (a) | FDR recording of cabin altitude Development of IR addressing safety recommendation GREC-2006-047 following Helios B737 accident. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Opinion
inv. | OPS.023 (b) | FDR recording of cabin altitude Development of AMC/GM addressing safety recommendation GREC-2006-047 following Helios B737 accident. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Decision
inv. | OPS.024 (a) | Restraint devices in a/c involved in parachute operations Development of IR addressing AAIB safety recommendation. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Opinion
inv. | OPS.024 (b) | Restraint devices in a/c involved in parachute operations Development of AMC/GM addressing AAIB safety recommendation. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Decision
inv. | OPS.027 (a) | Weight Survey – Adequacy of specified weights including baggage weight Transposed task from the JAA to review the standard weights due to demographic changes. Review of the Implementing Rules. | Method defined: Group | B9 | JAA Transfer | R3 | Group | Opinion
inv. | OPS.027 (b) | Weight Survey – Adequacy of specified weights including baggage weight Transposed task from the JAA to review the standard weights due to demographic changes. Development of AMC/GM. | Method defined: Group | B9 | JAA Transfer | R3 | Group | Decision
inv. | OPS.031 (a) | Loss of control - cargo loading errors Development of IR based on transfer of JAA task. |  | pre-RIA old format | JAA Transfer | R3 |  | Opinion
inv. | OPS.031 (b) | Loss of control - cargo loading errors Development of AMC/GM based on transfer of JAA task. |  | pre-RIA old format | JAA Transfer | R3 |  | Decision
inv. | OPS.038 (a) | Independent low height warning devices (e.g. RadAlt) for single pilot IFR CAT - aeroplanes Development of IR addressing safety recommendation UNKG-2006-103. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Opinion
inv. | OPS.038 (b) | Independent low height warning devices (e.g. RadAlt) for single pilot IFR CAT - aeroplanes Development of AMC/GM addressing safety recommendation UNKG-2006-103. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Decision
inv. | OPS.042 (a) | A person qualified to establish communication with ground emergency services present on board whenever a passenger is on board the aeroplane Transfer of JAA OPSG ongoing task in the IR. | Moved from the RMP 2010-2013 to the inventory |  | JAA Transfer | R3 |  | Opinion
inv. | OPS.042 (b) | A person qualified to establish communication with ground emergency services present on board whenever a passenger is on board the aeroplane Transfer of JAA OPSG ongoing task in AMC/GM. | Moved from the RMP 2010-2013 to the inventory |  | JAA Transfer | R3 |  | Decision
inv. | OPS.047 (a) | Clarification of separate runways definition Transfer of JAA OPSG ongoing task in the IR. |  | pre-RIA old format | JAA Transfer | R3 |  | Opinion
inv. | OPS.047 (b) | Clarification of separate runways definition Transfer of JAA OPSG ongoing task in the AMC/GM. |  | pre-RIA old format | JAA Transfer | R3 |  | Decision
inv. | OPS.049 (a) | Single engine piston helicopter operations over hostile environment Review of the Implementing Rules in order to set non-discriminatory requirements for operations over hostile environment and not allow only one technology (turbine engines). |  | pre-RIA old format | JAA Transfer | R3 |  | Opinion
inv. | OPS.049 (b) | Single engine piston helicopter operations over hostile environment Review of the AMC/GM in order to set non-discriminatory requirements for operations over hostile environment and not allow only one technology (turbine engines). |  | pre-RIA old format | JAA Transfer | R3 |  | Decision
inv. | OPS.050 (a) | Low visibility operations Transfer of JAA AWOSG open items/ongoing work in the IR. |  | pre-RIA old format | JAA Transfer | R3 |  | Opinion
inv. | OPS.050 (b) | Low visibility operations Transfer of JAA AWOSG open items/ongoing work in AMC/GM. |  | pre-RIA old format | JAA Transfer | R3 |  | Decision
inv. | OPS.054 (a) | Helicopter radio-altimeters Review of the IR's due to implementing/interpretation problems. |  | pre-RIA old format | Implementation problems | R3 |  | Opinion
inv. | OPS.054 (b) | Helicopter radio-altimeters Review of the AMC/GM due to implementing/interpretation problems. |  | pre-RIA old format | Implementation problems | R3 |  | Decision
inv. | OPS.056 (a) | Use of diagonal strap type harness safety belt for observer seats on older FAR certified aircraft Development of IR addressing poposal from CAA Sweden. |  |  | MS Request | R3 |  | Opinion
inv. | OPS.056 (b) | Use of diagonal strap type harness safety belt for observer seats on older FAR certified aircraft Development of AMC/GM addressing poposal from CAA Sweden. |  |  | MS Request | R3 |  | Decision
inv. | OPS.057 (a) | Transposition of JAA TGL43 HEMS mountain operations Transferred task from JAA. | Method changed (I) | B8 | JAA Transfer | R3 | Group | Opinion
inv. | OPS.057 (b) | HEMS mountain operations – Transposition of JAA TGL43 | Method changed (I) | B8 | JAA Transfer | R3 | Group | Decision
inv. | OPS.058 (a) | Senior cabin crew incapacitation Transposition of NPA-OPS 62 into Implementing Rules. |  | pre-RIA old format | JAA Transfer | R3 | Agency | Opinion
inv. | OPS.058 (b) | Senior cabin crew incapacitation Transposition of NPA-OPS 62 into AMC/GM. |  | pre-RIA old format | JAA Transfer | R3 | Agency | Decision
inv. | OPS.059 (a) | Carbon monoxide detector on board all GA aircraft Development of IR addressing safety recommendation FRAN-2002-001.13. |  |  | Air Accident Investigation recommendation | R3 |  | Opinion
inv. | OPS.059 (b) | Carbon monoxide detector on board all GA aircraft Development of AMC/GM addressing safety recommendation FRAN-2002-001.13. |  |  | Air Accident Investigation recommendation | R3 |  | Decision
inv. | OPS.060 (a) | Devices for reducing the effect of smoke and toxic fumes in large transport aircraft Development of IR addressing safety recommendation RUSF-2007-003. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Opinion
inv. | OPS.060 (b) | Devices for reducing the effect of smoke and toxic fumes in large transport aircraft Development of AMC/GM addressing safety recommendation RUSF-2007-003. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Decision
inv. | OPS.061 (a) | Flight crew training for go-around below DA/H (Aeroplanes) Development of IR addressing safety recommendation SPAN-2004-030. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Opinion
inv. | OPS.061 (b) | Flight crew training for go-around below DA/H (Aeroplanes) Development of AMC/GM addressing safety recommendation SPAN-2004-030. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Decision
inv. | OPS.062 (a) | Second pilot requirement for air ambulance flights with aeroplanes Development of IR addressing safety recommendation UNKG-2006-102. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Opinion
inv. | OPS.062 (b) | Second pilot requirement for air ambulance flights with aeroplanes Development of AMC/GM addressing safety recommendation UNKG-2006-102. |  | pre-RIA old format | Air Accident Investigation recommendation | R3 |  | Decision
inv. | OPS.063 (a) | Before the first flight of the day require the built-in test features of any installed CVR/FDR/FDAU to be monitored for correct operation Developing IR addressing safety recommendation UNKG-2008-020. |  | C2 | Air Accident Investigation recommendation | R3 | Group | Opinion
inv. | OPS.063 (b) | Before the first flight of the day require the built-in test features of any installed CVR/FDR/FDAU to be monitored for correct operation Developing AMC/GM addressing safety recommendation UNKG-2008-020. |  | C2 | Air Accident Investigation recommendation | R3 | Group | Decision
inv. | OPS.064 (a) | Commercial air transportation with certain Annex II aircraft Development of Implementing Rules for the commercial air transport operation of certain Annex II aircraft. | moved to the inventory from the RMP 2010-2013 |  | Basic Regulation | R3 | Group | Opinion
inv. | OPS.064 (b) | Commercial air transportation with certain Annex II aircraft Development of AMC/GM for the commercial air transport operation of certain Annex II aircraft. | moved to the inventory from the RMP 2010-2013 |  | Basic Regulation | R3 | Group | Decision
inv. | OPS.065 (a) | Review of equipment requirements Review of exemptions originating from EU-OPS/JAR-OPS and address ICAO recommendations in relation to the Implementing Rules. | moved to the inventory from the RMP 2010-2013 |  | Basic Regulation | R3 | Agency | Opinion
inv. | OPS.065 (b) | Review of equipment requirements Review of exemptions originating from EU-OPS/JAR-OPS and address ICAO recommendations in relation to the AMC/GM. | moved to the inventory from the RMP 2010-2013 |  | Basic Regulation | R3 | Agency | Decision
inv. | OPS.067 (a) | CoP aerial work: parachute ops, aerial application, display flying Review of Implementing Rules to better reflect industry best practices for certain 'aerial work' activities. | moved to the inventory from the RMP 2010-2013 |  | Basic Regulation | R3 | Group | Opinion
inv. | OPS.067 (b) | CoP aerial work: parachute ops, aerial application, display flying Review of AMC/GM to better reflect industry best practices for certain 'aerial work' activities. | moved to the inventory from the RMP 2010-2013 |  | Basic Regulation | R3 | Group | Decision
inv. | OPS.069 (a) | Tethered balloons Development of Implementing Rules for the operation of tethered balloons. | moved to the inventory from the RMP 2010-2013 |  | Basic Regulation | R3 | Group | Opinion
inv. | OPS.069 (b) | Tethered balloons Development of AMC/GM for the operation of tethered balloons. | moved to the inventory from the RMP 2010-2013 |  | Basic Regulation | R3 | Group | Decision
inv. | OPS.070 (a) | Helicopter performance class 3 IMC operations Development of Implementing Rules resulting from ICAO amendment. | moved to the inventory from the RMP 2010-2013 |  | ICAO alignment | R3 |  | Opinion
inv. | OPS.070 (b) | Helicopter performance class 3 IMC operations Development of AMC/GM resulting from ICAO amendment. | moved to the inventory from the RMP 2010-2013 |  | ICAO alignment | R3 |  | Decision
inv. | OPS.072 | Policy on flight continuation after in-flight shutdown |  | B9 | Air Accident Investigation recommendation | R3 | Group
inv. | OPS.075 (a) | Operator's description of non-revenue flights (IRs) | New task | B7 |  | R3 | Agency | Opinion
inv. | OPS.075 (b) | Operator's description of non-revenue flights (CS/AMC/GM) | New task | B7 |  | R3 | Agency | Decision
inv. | OPS.076 (a) | Cabin crew language skills for safety-related communications with passengers (IRs) | New task. Title changed (I) | B8 | Air Accident Investigation recommendation | R3 | Group | Opinion
inv. | OPS.076 (b) | Cabin crew language skills for safety-related communications with passengers (CS/AMC/GM) | New task. Title changed (I) | B8 | Air Accident Investigation recommendation | R3 | Group | Decision
inv. | 21057 | Extension of DOA privilege to approve minor revisions to Agency approved documents | Moved from RMP 2010-2013 to the Inventory - Issue covered by OSD | B8 | Industry request | R4 | Agency | Opinion
inv. | 26010 | Activation of ice protection - It amends the regulation applicable to operators of certain aerplanes used for CAT and certificated for flight in icing conditions. The proposed standards would require either the installation of ice detection equipment or changes to the Aeroplane Flight Manual to ensure timely activation of the airframe ice protection system. This proposed regulation is the result of information gathered from a review of icing accidents and incidents, and it is intended to improve the level of safety when aeroplanes are operated in icing conditions. |  |  | FAA harmonization | R4 |  | Decision
inv. | 145.020 | 145.A.45(e) It is felt that the possibility for operators to use work cards/sheets is confusing, contradicting the responsability of the Part 145 organisation to ensure good maintenance and has an adverse effect on the accomplishment of maintenance. Consideration should be given to amend the requirment to allow the use of operators work cards / sheets for daily inspections and line checks only. | No legal requirement for the TC holder to produce job cards. Task moved to the inventory (I) | pre-RIA old format | Safety related | R4 | Agency | Opinion
inv. | 20.003 (b) | Airworthiness and Operational Approval for on board equipment related to GPS (RNAV/GNSS) |  |  | Industry Request | R4 | Agency | Decision
inv. | 20.009 | Considerations for the Use of Airborne Separation Assistance Systems (ASAS): Development of Cockpit Display and Traffic Information and its data processors should be carefully followed with consideration of Human Factors issues, display symbology, flight deck integration, Crew procedures, training and the likely impact of certification procedures. |  |  | Industry request | R4
inv. | 20.012 | Electronic Control Systems for APUs: Update AMC 20-2 in line with changes made to AMC 20-3 for engines. (See CRD 04-2005 Comment 11) |  |  | MS request | R4
inv. | 20.013 | Thrust Control Malfunction (TCM): With the introduction of the concept of 'Thrust Control Malfunction (TCM)', it is considered that guidance on the certification issues associated with TCM should be included in AMC-20. (See CRD 04-2005 Comment 11) |  |  | MS request | R4
inv. | 20.015 | Installation of stretchers in aircraft certificated under JAR/CS 25.562 |  |  | MS request | R4
inv. | 21.004 | Critical Parts “Critical parts" is a concept used in Part 21 and also in various CS. However it is not very well developed in part 21 and not defined. Therefore the following issues need consideration and may lead to amendment of Part 21 and/or its AMC/GM:- Consider definition- the concept of “critical parts” needs better attention in Part 21- consistent approach necessary for all CS / EASA rules |  | pre-RIA old format | Industry Request MS Request | R4 | Group | Decision
inv. | 21.006 | Alternative procedure to DOA In Part 21 an alternative to DOA is presented to demonstrate capability for design. Is it necessary: - to formalize this alternative with a design capability certificate; and - to develop criteria for applying it. This will be reviewed and may lead to amendment of Part 21. |  |  | MS request | R4
inv. | 21.013 | 21A.51, 21A118A, 21A.619 TC / STC / ETSO authorisation validity A review of the (legal) consequences of - invalidity of the above Certificates; and - Consequences of TC surrender and transfer may lead to amendment of Part 21 and/or its AMC/GM. |  | pre-RIA old format | Certification request | R4 | Agency | Opinion
inv. | 21.016 | Part storage instructions A proposal to add a requirement for TC holders etc. to provide instructions for storage of parts will be reviewed and may lead to amendment of Part 21 and/or its AMC/GM. |  | pre-RIA old format | MS request | R4
inv. | 21.019 | One-off Supplemental Type certificates (STCs) The objective is to introduce more flexibility with regard to the demonstration of capability (21A.112B) for the design of “one-off” STCs and to make the related amendments of Part 21 and/or its AMC/GM. |  | pre-RIA old format | MS request | R4
inv. | 21.022 | 21A.163 POA privileges Proposals to: - Extent the maintenance privilege (21A.163(d)) to other products and parts and in time; and - make Conditions for issuance of C of A for new aircraft (21A.183(1)(ii)) consistent with the POA privilege,will be reviewed and may lead to amendment of Part 21 and/or its AMC/GM. |  | pre-RIA old format | Industry Request | R4 | Group | Opinion
inv. | 21.031 | Subpart Q; Identification of products parts & appliances Proposals to - clarify the objective of marking: - clarify retention of records related to marking of critical parts; - take into account the engine (CS E-110) requirements for marking; - limit the requirement to mark parts with name, trademark of 21A.804(a)(1) as in (a)(2). |  | pre-RIA old format | MS request | R4
inv. | 21.044 | Foreign Supplier Surveillance Make AMC and GM consistent with rules for international cooperation |  |  | MS request | R4
inv. | 21.045 | ETSO authorisation holder Reconsider why design and production should be one legal entity |  | pre-RIA old format | Industry request | R4
inv. | 21.048 | On-board or Field Software Loading and Part Number Marking: The subject covered in new AMC 20-3(10) (d) is a post-TC activity and may be more appropriately presented in AMC to Part 21 for example. (See CRD 04-2005 Comment 21) |  |  | Industry request | R4
inv. | 21.054 | Direct shipment authorisation |  |  | Industry request | R4
inv. | 22.002 & 22.003 | Flutter and Turbo Charged Powered Sailplanes and reductio of Vne with altitiude - Reduction of the never exceed speed with altitude to maintain the safety margin before flutter - The installation of turbo charged (or de-rated) engines makes it possible that high speeds may be maintained up to high altitudes. The gap between VH and flutter speed might decrease. |  |  | Safety related | R4
inv. | 22.005 | Electronic engine control systems The intent is to update the requirements in accordance with the state of the art, to cover new developments |  |  | Industry request Certification request | R4
inv. | 22.007 | Stall warning devices |  |  | Safety related | R4
inv. | 22.008 | Jet powered sailplanes |  |  | Industry request | R4
inv. | 23.002 | Windshield Bird Strike Improve windshield resistance to bird strike. Preparatory work consists of review of existing data. |  |  | Safety related | R4
inv. | 25.013 | Bird Strike Damage In the light of development in Engine certification, taking into account the general increase of weight in bird population and the faster approach procedures, the issue deserves to be revisited. Preparatory work consists of a review of existing studies and the development of a regulatory impact assessment. | Moved from RMP 2010-2013 to the Inventory - Issue covered by the Certification memos | pre-RIA old format | Safety related | R4 | Group | Decision
inv. | 25.018 | Fire Protection of Engine Mounts, Flight Controls and Other Structure |  |  | Safety related | R4
inv. | 25.025 | Terrain Awareness and Warning Systems (TAWS): Amend CS 25.1581-1587 (Airplane Flight Manual) to reflect requirements for appropriate TAWS procedures (e.g. for the use of the equipment, proper flight crew action with respect to the equipment, and deactivation for planned, abnormal, and emergency conditions), and an outline of all input services that should be operating. |  | pre-RIA old format | Safety related | R4
inv. | 25.032 | Amend CS 25.1581-1587 (Airplane Flight Manual) to reflect requirements for appropriate TAWS procedures (e.g. for the use of the equipment, proper flight crew action with respect to the equipment, and deactivation for planned, abnormal, and emergency conditions), and an outline of all input services that should be operating. | Updating in the description of the task | pre-RIA old format | Safety related | R4
inv. | 25.037 (b) | Avionics Phase 2 Development of additional Appendices to AMC 25-11 covering HUD, EVS and SVS. Group |  | pre-RIA old format | Safety related Industry request | R4
inv. | 25.038 (a) | Human centered design (step 1) The intent is to add new paragraph 25X4 (Human error) that would require: To show by analysis, substantiated where necessary by test, that as far as reasonably practicable all design precautions have been taken to prevent hu |  | pre-RIA old format | Safety related | R4 | Group | Decision
inv. | 25.038 (b) | Human centered design (step 2) |  | pre-RIA old format | Safety related | R4 | Group
inv. | 25.043 | Burn-through resistance of fuselage In the current situation, external fuel fed fires will typically enter the aircraft interior within 10-60 seconds after initiation of fire. With the addition of burn through resistance measures, this time could be extended to 3 minutes, giving much more time for escape. Preparatory work will include the development of a Regulatory Impact Assessment. |  |  | Safety related | R4
inv. | 25.046 | Seat pitch: All ins and outs on the issue of minimum seat pitch need to be investigated, including the potential relations to Deep Vein Trombosis. More research may need to be done to find out the details. Research and preliminary RIA mandatory before starting rulemaking. |  | pre-RIA old format | Health and Safety related | R4
inv. | 25.047 | Overhead bin safety precautions Develop a new AMC to CS 25.787 (Seats, berths, safety belts and harnesses) to mitigate risks from overhead bins. |  | pre-RIA old format | Safety related | R4
inv. | 25.054 | Engine Cowl Latching: There are two major elements contributing to the cowl latching in-service experience: maintenance's ability to properly latch and the actual design of the latch. |  | pre-RIA old format | Safety related | R4
inv. | 25.061 | Flight issues to address operational needs - Landing in Abnormal Configurations: Prepare harmonized CS/FAR 25 and AMC/AC to give guidance on the presentation of landing distance information and procedures applicable to landing in abnormal configurations that should be included in the Flight Manual. - Go-around Performance: Review CS paragraphs addressing go-around performance and procedures. | Task description changed since “Steep approach landings, based on NPA 25B-267FR” is covered by task 25.070 | pre-RIA old format | Safety related MS Request | R4
inv. | 25.062 | Vibration, Flutter and Aeroelastic Stability CS25.629: Flutter, deformation and failsafe criteria, details the requirements to be complied with under various conditions. However, AMC material to CS 25.629 does not address Limit Cycle Oscillations in sufficient detail. |  | pre-RIA old format | Certification request | R4
inv. | 25.063 | Portable electronic devices (PEDs) |  |  | Safety related | R4
inv. | 25.065 | New CS 23 and CS 25 rules for seaplanes (all kinds of flying boats, floatplanes and amphibians as well as wing-in-ground effect craft [Category C]) |  |  | Stakeholder request | R4
inv. | 25.066 | Possible changes to structural design requirements: Specific topic raised were; new fail safe/damage tolerance requirements and protection from engine rotor burst involving failure of multiple disks. |  |  | Safety related | R4
inv. | 25.068 | Class E Cargo Compartments – Essential Systems Fire Protection |  |  | Safety related | R4
inv. | 25.071 former OPS.032 | Consideration for Power Controlled A/C Concept (total loss of primary controls) |  |  | JAA Transfer | R4
inv. | 25.072 former OPS.036 | Real weight and balance of an aircraft Proposal from DGAC following incidents/accidents due to incorrect load data and loading. |  |  | Air Accident Investigation recommendation | R4
inv. | 25.073 former OPS.037 | Contrast and conspicuity of wing surface escape markings Review the design, contrast and conspicuity of wing surface markings associated with emergency exits on Public Transport aircraft, with the aim of ensuring that the route to be taken from wing to ground is marked unambiguously. |  |  | Air Accident Investigation recommendation | R4
inv. | 25.074 | Analysis of on-ground wings contamination effect on Takeoff performance degradation |  |  | Safety recommenadtion | R4
inv. | 26.007 | Security Based on task 25.057 and resulting amendment to CS-25, 26.007 aims at studying the need to have additional airworthiness requirements for operations. Envisaged deliverable: Decision amending CS-26 (if appropriate). |  |  | MS request | R4 | Agency | Decision
inv. | 26.009 | Introduction of FDR and CVR improvements Consistently with task MDM.068, this task will address the introduction in production of FDR and CVR improvements in harmonisation with FAA final rule docket n° FAA-2005-20245. It will also consider the introduction of maintenance requirements for in-service and production aircraft, as reminded per SIB 2009-028 in December 2009. This should be performed in coordination with the newest developments at ICAO level regarding FDR/CVR maintenance requirements. |  |  | Safety recommendation | R4
inv. | 27&29.010 | Equipment systems and installations. As a result of harmonisation work: - Develop 27.1309 AMC to address IFR and VFR operations with complex systems whose failures are not hazardous or catastrophic. - Review 27/29.1309 and provide consistent terminology and failure condition categories with accepted aerospace standards - clarify and update various aspects of the AC/AMC material associated with CS-29. - consider complex systems whose failure may be hazardous or catastrophic. |  |  | Industry request | R4
inv. | 27&29.017 | Rotorcraft rotor & transmission It is considered that the current advisory material could be enhanced to ensure a standardised approach and to provide better guidance on how to use design assessment results to establish appropriate compensating features where necessary. |  |  | Safety related | R4
inv. | 27&29.020 | Vibration Health Monitoring (VHM): CS 27&29 (Book 1) rulemaking task to adopt ICAO recommendations on the fitment of VHM systems to helicopters, defining the applicability of helicopters and operations affected and to define the scope of VHM to be required. |  |  | Safety related | R4
inv. | 27&29.021 | Rotor brakes / Rotor brake controls |  |  | MS request | R4
inv. | 27&29.022 | Pilot compartment view |  |  | MS request | R4
inv. | 27&29.024 | Night vision imaging system |  |  | Industry request | R4
inv. | 27&29.025 | PCDS |  |  | Industry request | R4
inv. | 27&29.026 | Additional requirements for helicopters operating to or from helidecks located in a hostile sea area - feature to prevent snagging with safety nets |  |  | MS request | R4
inv. | 27&29.028 | Pilot control forces |  |  | Safety recommendation | R4
inv. | 30.001 | Transport Airships Development of the Certification Specifications for airships (CS-30T) |  | pre-RIA old format | Industry Request | R4 | Group | Decision
inv. | 30.002 | Normal/ Commuter Airships: Development of the Certification Specifications for airships (CS-30N) |  | pre-RIA old format | Industry Request | R4 | Group | Decision
inv. | 31.002 | Hot-Air Airships Development of the Certification Specifications for hot-air Airships (CS-31HA) |  |  | Industry request | R4 | Group | Decision
inv. | 66.013 | 66.A.50 Medical drugs and alcohol policy needs to be clarified. This is a complex issue as the approach varies from country to country. | Moved from RMP 2010-2013 to the Inventory - Ending date was 2016.01 |  | Safety related | R4 | Group | Opinion
inv. | 66.016 | Appendix I and II Tables need to be developed in light of technological advancements including ATA chapter re-numbering / questions and number of answers and the question databank. |  |  | MS Request | R4 | Group
inv. | 66.018 | Appendix I and II Requirements need to be developed to avoid the split of basic modul examinations. |  | pre-RIA old format | MS Request | R4 | Group
inv. | AWO.008 | Category II/III GNSS Landing System Development of the necessary changes to CS-AWO to support GNSS Landing System Category II/III approach and landing. |  |  | Industry request | R4
inv. | BR.011 | Revision of the Basic Regulation in relation with 'aviation fluids'. An A-NPA will discuss this need. This was triggered by the issue of ant-ice and de-ice fluids. |  |  | Safety related | R4
inv. | E.002 | Engine imbalance loads This task aims at improving CS-E 520 (c)(2) (Strength: shedding of compressor or turbine blades) using JAA NPA 25- 305 and 306. (See also task 25.015 and 25.016) |  | pre-RIA old format | Safety related | R4 | Agency | Decision
inv. | E.003 | Fan blade off Improvement of CS-E 810 (compressor and turbine blade failures) |  | pre-RIA old format | Safety related | R4
inv. | E.005 | 150 h endurance test Improvement of CS-E 740 (Endurance tests) to overcome current problems during certification of engines |  | pre-RIA old format | Certification request | R4
inv. | E.008 | Safety Analysis for piston engines: Preparatory work consists of the review of comparable requirements for Turbine Engines. Safety Analysis is an important requirement for engine safety, |  | pre-RIA old format | Safety related | R4
inv. | E.012 | Mandating Limits for Time-Limited Dispatch: The TLD limitations are EASA approved, and can not be changed without EASA approval. They need to be placed into the airworthiness limitations section of the ICA so that have special significance and cannot be changed without EASA approval. (See CRD 03-2005 Comment 74) |  |  | MS request | R4
inv. | E.016 | Engine Rotor Integrity The engine community, including both US and European manufacturers, and led by the FAA, have for some years been undertaking research and developing enhanced AC material under the RISC (rotor integrity sub-committee) activities, to address structural issues relating to engine rotors (e.g. hard alpha inclusions, high energy rotor DT, etc.) This task aims to review and adopt the output from the RISC activities. |  |  | Industry request | R4
inv. | ETSO.010 | ETSO C16a update - Electrically Heated Pitot and Pitot-Static Tubes |  |  | Safety related | R4
inv. | GYR.001 | Gyroplane |  |  | Industry request | R4
inv. | M.020 | Revision of written procedure covering the elimination of reported faults on flight control of any system failure when subjecting vital flight control systems to trouble shooting |  |  | Safety related | R4 | Group | Decision
inv. | M.024 | The CAME Part 1, AMC Appendix V or M.A.704 or M.A.708 makes very little > reference to Operational approvals such as AWOPS, RVSM, ETOPS etc. It was believed that this was covered on Surveyor training but seems to be not covered in the requirement other than through JAR OPS legislation. |  | pre-RIA old format | MS Request | R4 | Group
inv. | M.026 | Omission of M.A.801 c in the definition for: controlled environment |  |  | MS Request | R4 | Group | Opinion
inv. | MDM.001 (b) | Long Range Operations (LROPS): The A-NPA will explore the need for, and possible content of LROPS requirements. |  |  | Safety related | R4 | Agency
inv. | MDM.006 | 21A.174, 21B.320, Part M; Inspection requirements for CofA and ARC The proposals to ensure consistency of inspection requirements for Certificate of Airworthiness and Airworthiness Review Certificate will be reviewed and may lead to amendment of Parts 21, M and/or their related AMC/GM.This task is linked with 21.041. |  | pre-RIA old format | MS Request | R4 | Group
inv. | MDM.017 | Appendices Guidance material should be developed on the proper manner to fill in the forms contained in the appendices. |  | pre-RIA old format | MS Request | R4 | Agency | Decision
inv. | MDM.025 | Lightning: Harmonization activity on CS/FAR xx.1316 and associated AC/AMCs on lightning (environment, zoning, direct effects, indirect effects, fuel) For CS-23, -25, -27 and -29 |  | pre-RIA old format | Safety related | R4
inv. | MDM.031 (c) | Commercial Air transportation operations Single Engine IMC Implementation of CS-23 SE-IMC Appendix. |  |  | Industry request | R4 | Group | Decision
inv. | MDM.050 | Pilot Intervention Time Following Power Failure in Single-Engine Helicopters. Modification to Rule CS-VLR.143(d) and CS-27/29.143(d) - Controllability & Manoeuvrability. |  |  | Safety related | R4
inv. | MDM.051 | CVR Recording Quality Development of AMC/GM addressing safety recommendation. |  |  | DGAC proposal | R4 |  | Decision
inv. | MDM.052 | Fuel Cells |  |  | Industry request | R4
inv. | MDM.066 | Special requirements for aeroplanes in private use only (Adaptation of CS-25 and CS-23 and AMC to CS-25 and CS-23) |  |  | Industry request | R4
inv. | MDM.067 | Flight data recording: Transmission via real time data link |  |  | Stakeholder request | R4
inv. | MDM.068 | Revision of FDR and CVR certification specifications This rulemaking task will revise FDR and CVR certification specifications in harmonisation with FAA final rule docket n° FAA-2005-20245; the main improvements to be addressed are: - data link communications recording, - the requirement that no single electrical bus failure terminates the recording on both CVR and FDR (ref SR UNKG-2005-074), - the requirements that the CVR and cockpit area microphone are provided with an independent 10 minute back-up power source, to which the CVR and cockpit area microphone are switched automatically, in the event that normal power is interrupted (ref SR UNKG-2005-075), - the requirement of separate containers for aeroplanes CVR and FDR. Refer to SR UNKG-2005-074 and UNKG-2005-075 issued on 16/09/2005 "Incident to Airbus A320-214 registered G-BXKD, on 15.01.2005 at London Gatwick Airport, West Sussex" In addition, CS XX.1457 and XX.1459 should be reviewed and at least the AMC should be amended to highlight the maintenance requirements, as reminded in SIB 2009-028 in December 2009. This should be performed in coordination with the newest developments at ICAO level regarding FDR/CVR maintenance requirements. Refer also to BEA study recommendations dated May 2005. This task will address CS-23, CS-25, CS-27, CS-29. |  |  | Safety recommendation | R4
inv. | MDM.074 | Emergency Locator Transmitters - installation, location and de-activation 1) Incorporate, in the aircraft Certification Specifications, provisions to enforce installation requirements as provided in ED-62A standard. The objective is to ensure that the signal between the ELT unit and the antenna is not disrupted after a crash. Indeed, several crash accidents occurred when the signal was not transmitted because either the cable between the unit and the antenna was destroyed, or the unit was separated from the antenna, or the antenna was separated from the unit. Refer to SR GERF-2009-019 triggered from BFU letter entitled “Reliability of 406 MHz emergency locator transmitters (ELT) in aircraft”. 2) Incorporate provisions in the aircraft Certification Specifications to require that information on the location and de-activation of required ELTs is readily available onboard the aircraft. This requirement is applicable to automatic ELTs that are rigidly attached to the aircraft and not deployable.Refer to SR IRLD-2009-002. |  |  | Safety related | R4
inv. | MDM.077 | Release of works performed under D1 approval rating Additional information is required for the release of works performed under D1 approval rating (use of EASA Form 1) | New task |  |  | R4
inv. | MDM.079 | First installation of an STCs by a maintenance organisation to show compliance when the STC is not yet approved | New task |  |  | R4
inv. | MDM.080 | Quality manager's requirements on part-M and part-145 organisations Clarification of personnel requirements for Part-M organisations; clarify who is the person mention in M.A.706 (c); Clarify whether or not the postholder as defined in M.A.706 (d) can | New task |  |  | R4
inv. | MDM.084 | Aligment with 21.026 Acceptance of new categories of parts for which EASA form 1 is not required | New task |  |  | R4
inv. | TR.001 | Tiltrotor |  |  | Industry request | R4
inv. | VLA.002 | Test Factors for Composite Structures Clarify that the special factors case of CS-VLA 619 (c) is not restricted solely to composite structures. |  |  | MS request | R4
inv. | VLA.007 | To include the following aspects in one general update of CS VLA: ~ Manouvering speed ~ Airspeed indicator ~ Powerplant instruments ~ Accesibility ~ Review of CS VLA 441, 443, 611, 1545(a), 1549 & 1507. Purpose is to review developments in CS(JAR) 22 & 23 since adoption of JAR VLA. Other proposals whether they are appropiate for CS VLA, taking into account their general intended safety level. There is a link with VLA.001, 003, & 005. |  |  | MS request | R4
inv. | VLR.001 | Applicability of CS-VLR: New initiative to expand the applicability of CS-VLR to include rotorcraft with a mass included between 600 kg and 750 kg. |  | pre-RIA old format | Industry request | R4
inv. | ATM.006 | Airspace users requirements |  |  | Basic Regulation | R5 | Group
inv. | ATM.010 | Carriage of ACAS II equipment on aircraft other than aeroplanes in excess of 5700kg or 19 Pax | New task (I) |  | Industry request | R5 | Agency | Opinion
inv. | ATM.020 | Study on turbulences in public transportation |  |  | Safety recommendation | R5 | Group
Note on B54: Elina Zheleva: ex OPS.026
Note on B55: Elina Zheleva: ex OPS.026
Note on B56: Elina Zheleva: ex OPS.027
Note on B57: Elina Zheleva: ex OPS.027